# IPHC Research Program:

# Review of 2006 Projects and Proposals for 2007

The International Pacific Halibut Commission Staff

January 16, 2007

## Introduction

This document reviews research conducted by the IPHC staff in the past year and proposed for the upcoming year. The report is divided into two sections, with the first section reviewing the status of research projects conducted 2006. The second section presents the preliminary staff research proposals for 2007. Information is provided on when each project was initiated, the anticipated completion date, the annual cost, a description of the costs, and the purpose of the project. This report does not include ongoing staff tasks such as data collection and processing that are necessary for the management of the fishery.

Research projects are organized into three funding categories that reflect availability and source of research funds. Limited research requiring direct financial support from the Commission is possible under the basic $3.797 million (as of 2006) government appropriations, although a number of programs can be conducted using only the staff resources that are supported by the appropriations. The three funding categories are:

- Funded Research: Necessary research projects of high priority that can only be conducted with revenues generated by survey fishing in 2007, and/or carry-over from 2006;

- Contracts and Grants: Agreements with other parties to conduct specific research. In this case, contracts and grants are shown for projects where the IPHC staff is the principle investigator; and

- Research conducted without direct funding: Necessary research projects of high priority that can be conducted within the IPHC budget.

Nearly all of the research done by the staff is directed toward one of three continuing objectives of the Commission:

i) Improving the annual stock assessment and quota recommendations;

ii) Developing information on current management issues; and

iii) Adding to knowledge of the biology and life history of halibut.

In each of these areas our routine work program applies the best information and methods available, and our research program aims to improve the information and methods by answering the most important outstanding questions.

## SECTION I:

## REVIEW OF RESEARCH CONDUCTED IN 2006

Research conducted by the IPHC staff during 2006 continued in three basic areas:  life history, fish movements, and general biology. Most of the projects were conducted as part of the normal staff duties, with no additional funding required outside of staff salaries. Funding for projects outside of staff salaries came from supplemental funding, and these projects are outlined below.

## Funded Research in 2006

The dockside detection program (Project 413) conducted by IPHC scan samplers continued in 2006, with samplers in eight Alaskan and four B.C. ports. Additionally, IPHC received state and tribal assistance in scanning in nine ports in Washington and Oregon. Through 29 October, over 29 million pounds (46% of total landings) have been scanned. The number of tags recovered in 2006 totals 407 from the 2003 primary experiment and 244 from the 2004 secondary experiment. Additionally, recoveries from a double tag experiment designed to estimate PIT tag shedding rates continue to show a shedding rate of two percent, well within the projected and acceptable range for the experiment. Scan sampler tag detection and fish counts are routinely tested. Results have shown that scan sampler fish counts are quite accurate, approaching 99% agreement, which is crucial to being able to estimate exploitation rates, the goal of the PIT tag project. Scanning success rates in tag seeding tests were found to vary somewhat by sampler but were generally quite high (96-100%), indicating that scan samplers were missing few, if any, tags. In general, results in 2006 are consistent with those from previous years and have offered no additional insights on the low recovery rates in the central/western Gulf and Bering Sea areas. Scanning is currently planned to conclude in 2008.

The Otolith Elemental Fingerprint (OEF) project (#620) has shown that, using age-2 halibut from western Alaska, the chemical composition of otoliths can be used to successfully distinguish and classify individuals within general geographic regions (Bering vs. Kodiak vs. Cook Inlet), with 80-90% accuracy. The spatial model developed over the last two years relies primarily upon oxygen and carbon isotope ratios and secondarily upon trace element data, thus completing the first phase of the project which was simply a proof of concept. During FY 2006 we conducted trace element analysis on otoliths collected from southeast Alaska which will be used to examine temporal stability and variance associated with increasing sample sizes. Stable carbon and oxygen analyses still need to be conducted for these fish; otoliths will be forwarded to Woods Hole Oceanographic Institute by year-end. The second phase of the project will seek to establish appropriate protocols and sampling sites so that a coastwide nursery "otolith element map" can be developed.

Genetics (Project 621) sample analysis continued in 2006 under the supervision of Dr. Lorenz Hauser at the University of Washington’s Marine Molecular Biology Laboratory. Two sets of tissue samples were analyzed for variation in nuclear microsatellite diversity: a subset of samples collected during winter charters in 2004 near Queen Charlotte Island, Portlock Bank, and Pribilof Canyon, and a limited number of samples from a much more extensive collection (~1,900 tissue samples were collected from 20 sites) conducted during the 2005 setline survey.

Analysis of the winter samples has been completed and a formal report presented to the IPHC by Dr. Hauser. The results indicate rather small degrees of genetic divergence among sites which suggests a homogenous population with respect to gene frequencies, but some between-site differences tend to be statistically significant which simultaneously suggests a certain degree of genetic isolation among areas. Additionally, a number of alleles have been encountered which are much more common in females than in males, which is intriguing in two respects. It suggests that we may be able to develop genetic techniques to non-lethally determine sex, but it also means that genetic population analyses need to be conducted in either a sex-specific manner or after exclusion of sex-linked genes. This demands that larger sample-sizes be used for population analysis. Not all of the 2004 winter samples have been analyzed due to time constraints; in 2007 we will endeavor to screen the remaining samples to improve the strength of the population analyses. In addition, we released a charter bid request to re-sample the same winter spawning grounds in winter of 2007. Re-sampling is required because the relative low among-site genetic divergences beg the question: are differences between regions greater than differences due to natural genetic drift? Answering this question is critical to understanding the meaning of the “significance” of between-site differences. In addition, a total of 245 samples collected in 1998-99 at Langara Island (2B) and Portlock (3A) are being analyzed. These should add additional information on temporal drift, although they will do nothing to help us understand potential segregation between the Gulf of Alaska and southeast Bering Sea.

Of the ~1,900 samples collected during the summer of 2005, only 255 have been analyzed to-date. These samples are being analyzed in an attempt to gain further resolution of differences observed during the pilot study completed in 2004 (these results are now available as IPHC Scientific Report #81). During that study we observed greater genetic difference between the eastern Aleutian Islands (Adak) and the southeast Bering Sea (St. Paul Island) than between the southeast Bering Sea and Oregon. This led us to hypothesize that there may be more mixing between the Gulf of Alaska and the southeast Bering Sea shelf than between the Aleutian Islands and other regions. We have begun the analysis of additional summer samples using sites positioned east-to-west from the western Alaska Peninsula into the Aleutians in hopes of detecting potential segregation between Areas 3 and 4. Lab work has been completed, but the quantitative statistical analysis of observed gene frequencies is still under way. It should be noted that even if segregation really does exist along the Aleutians, we may not be able to detect it using summer samples. Reproductive isolation is defined by spawning stock structure, which is established during winter, and a full understanding of potential Aleutian isolation will probably require that at some point we sample the Aleutians in winter.

PAT tags were released in two experiments in 2006:  a group of 78 in Areas 2A/2B (Project 646), and 24 in Areas 4A/4D (Project 640). The former was the outcome of discussions at the 2006 Annual Meeting, which sought to provide further information on summer to winter seasonal movements of fish in those areas. These tags are scheduled to pop up during February-March, 2007 at two week intervals. The latter set of releases was also designed to identify seasonal movements and will pop up in mid-February, 2007.

A pilot study on use of internal archival tags in halibut began in 2006 (Project 650). This initial work represents a controlled test of the relative utility of three different models of internal archival tag that can be used on relatively small (60-99 cm) halibut. In August 2006, twenty four halibut ranging from 65-90 cm were captured aboard the F/V Heidi Sue and transported live to the Oregon Coast Aquarium in Newport. The fish were then held for a period of 80 days to allow them to recover from transfer stress, resume normal feeding activity, and heal all visible capture wounds. On October 19 and 20, surgery was conducted to implant internal archival tags into 15 of the study specimens. Five fish were tagged with each of 3 different tag varieties: 1) Lotek LTD 1110, an 11 mm by 32 mm resin-body tag, 2) Lotek LTD 2310, a 16 mm by 76 mm silicon-coated stainless steel tag with a 24 cm external light stalk, 3) Wildlife Computer MK9, a 17 mm by 67 mm resin-body tag with a 19 cm external light stalk. All tag varieties record temperature and depth, and the tags with light stalks are capable of recording ambient light for the purpose of estimating fish location. All fish survived the implantation process, resumed feeding very shortly after surgery, and are showing signs of incision closure. The fish will be held until early 2007 in order to monitor their recovery, after which they will be sacrificed and examined internally to assess any potential reactions to the internal tag, and to determine the feasibility of non-invasive sex determination via veterinary ultrasound.

An experiment (Project 648) was conducted during early June, 2006 to examine the ability of traps to catch halibut but which have minimal bycatch of rockfish. The field effort, which took place around Cape St. James in Area 2B, utilized the newly emerging Didson sonar technology to observe fish behavior around a baited sablefish trap. The purpose of the experiment was to try different trap modifications and determine their effect on the capture rates of halibut and rockfish. The experimental frame was set 37 times, with total observed bottom time at just over 73 hours. Very low catch rates for both halibut and rockfish precluded modifying and testing entrance and escape rings to evaluate trap modifications. We observed one escape of a rockfish which entered via the entrance tunnel, and escaped via an escape ring prior to gear retrieval. One rockfish escaped through an escape ring during gear retrieval. This compares to three rockfish which were captured and did not escape in the acoustical trap. Although we were not able to evaluate trap modifications to change catch rates, the trip was a success in terms of the performance of the Didson and associated gear. Additional funding for the project was provided by Pacific Halibut Management Authority (PHMA).

In 2006, IPHC and Washington Department of Fisheries received funding from Pacific States Marine Fish Commission (PSMFC) to connect a join project with industry (Project 649). The Area 2A summer assessment charter was expanded to included 25 special stations in the Washington survey region to look at rockfish populations. Station locations where selected by WDFW in an effort to better characterize rockfish abundance. Stations were selected with the hope of targeting more rocky bottom than the standard survey stations in the Washington region. Three skates of gear where fished at each station as a precautionary approach due to the exploratory nature of these stations and concerns of over fishing yelloweye rockfish. Activities at each station were identical to those on standard IPHC stations, and all rockfish were tagged for identification and further sampling upon offload. A summary of this project will be submitted to PSMFC by the end of November 2006. Depending on those results, there may be a second season of sampling under this funding opportunity, although station positions may be changed to better characterize rocky bottom type.

In Project 644, Archipelago Marine Research, Ltd. (Victoria, BC) was contracted to investigate the use of video monitoring technology in the groundfish trawl catcher processor fleet operating in the Bering Sea. This pilot study involved field testing a digital video monitoring system consisting of nine closed circuit television cameras, GPS, and on-board data storage. Cameras were installed in key fish handling areas, providing a full view of trawl deck and closer views of the interior factory and discard chutes. Using the series of cameras installed throughout the factory, individually tagged halibut were tracked through the factory sorting process to discard. The tests using video monitoring equipment provided promising results for the use of this technology. The system performed reliably and provided the scientific personnel and vessel crew with a useful real-time monitoring tool. Post-cruise data analysis demonstrated that halibut were readily detectable throughout the factory. However, imagery was not suitable for making detailed assessments of catch composition. We believe that video monitoring offers opportunities to improve observer’s abilities to monitor catch on factory trawlers. Further work is needed to evaluate the benefits of video monitoring in terms of the various monitoring issues in the fishery and decide on appropriate specifications for the equipment, how it should be configured, and appropriate methodology for use of video data. In particular, the need for careful consideration for the data issues surrounding the use of this technology was highlighted. The results will be published as an IPHC Technical Report in 2007.

Finally, IPHC hired one intern (Project 618) in 2006. Ms. Jessica Hobden (University of Victoria) worked May-August on a project titled “A one dimensional spatial analysis of Pacific halibut (Hippoglossus stenolepis) on longline gear testing for aggregations based on sex and length”, which gave her an opportunity to spend time on a survey vessel collecting data. She presented his results to the staff, and her final report will be included in the 2007 RARA.

## 2006 Contract Research

NMFS Auke Bay Lab (ABL) has had a sablefish data collection program for several years and IPHC has assisted NMFS with the program. In 2003/2004, the program was reviewed and modified to meet the IPHC confidentiality policy and to encompass all vessels rather than just vessels greater than 60 feet. Under a Statement of Work (SOW), NMFS contracts IPHC to collect and review information on sablefish catches (Project 628) during the IPHC port sampler’s logbook interview. Sablefish data are entered by IPHC staff, edited, and an electronic summary provided to the NMFS ABL scientists. Vessels are assigned a unique code in the summarized data to preserve confidentiality. The SOW was renewed for 2006.

IPHC also received a grant from NMFS for the incremental increase in port sampling costs due to the IFQ program (Project 375).

# 2006 Research Publications

IPHC staff noted in Bold type.

Chen, D-G. and Hare, S.R. 2006. Neural network and fuzzy logic models for Pacific halibut recruitment analysis. Ecol Modeling, 195: 11-19.

Clark, W.G., and Hare, S.R. 2006. Assessment and management of Pacific halibut:  data, methods, and policy. Int. Pac. Halibut Comm., Sci. Rep. 82, 81 p.

Clark, W.G., and Kaimmer, S.M. 2006. Estimates of commercial longline selectivity for Pacific halibut (Hippoglossus stenolepis) from multiple marking experiments. Fish. Bull. 104:465-467.

Foy, R.J., Crapo, C.A., and Kramer, D.E. 2006. Investigating the roles of temperature and exercise in the development of chalkiness in Pacific halibut. Int. Pac. Halibut Comm., Tech. Rep. 50, 24 p.

Hauser, L., Spies, I., and Loher, T. 2006. Microsatellite screening in Pacific halibut (Hippoglossus stenolepis) and a preliminary examination of population structure based on observed DNA variation. Int. Pac. Halibut Comm., Sci. Rep.  81, 28 p.

Lehodey, P., Alheit, J., Barange, M., Baumgartner, T., Beaugrand, G., Drinkwater, K., Fromentin, J-M., Hare, S.R., Ottersen, G., Perry, R.I., Roy, C., van der Lingen, C.D., and Werner, F. 2006. Climate variability, fish and fisheries. J. Climate 19: 5009-5030.  DOI: 10.1175/JCLI3898.1

Loher, T., and Seitz, A. 2006. Seasonal migration and environmental conditions experienced by Pacific halibut (Hippoglossus stenolepis), elucidated from Pop-up Archival Transmitting (PAT) tags. Marine Ecology Progress Series, 317:259-271.

Loher, T., and Seitz, A. 2006. Seasonal migration and environmental conditions experienced by Pacific halibut in the Gulf of Alaska, elucidated from Pop-up Archival Transmitting (PAT) tags. Int. Pac. Halibut Comm., Sci. Rep. 82, 40 p.

Sadorus, L. 2005. Pacific Halibut:  Flat or fiction? International Pacific Halibut Commission, Seattle, WA.

Sullivan, P.J., Breidt, F.J., Ditton, R.B., Knuth, B.A., Leaman, B.M., O’Connell, V.M., Parsons, G.R., Pollock, K.H., Smith, S.J., and Stokes, S.L. 2006. Review of Recreational Fisheries Survey Methods. National Research Council of the National Academy of Sciences. National Academy Press, Wash. DC. 187p.

Trites, A.W., Miller, A.J., Maschner, H.D.G., Alexander, M.A., Bograd, S.J., Calder, J.A., Capotondi, A., Coyle, K.O., Di Lorenzo, E., Finney, B.P., Gregr, E.J., Grosch, C.E., Hare, S.R., Hunt, G.L., Jahncke, J., Kachel, N.B., Kim, H., Ladd, C., Mantua, N.J., Marzban, C., Maslowski, W., Mendelssohn, R., Neilson, D.J., Okkonen, S.R., Overland, J.E., Reedy-Maschner, K.L., Royer, T.C., Schwing, F.B., Wang, J.X.L., and Winship, A.J. 2006. Bottom-up forcing and the decline of Steller sea lions in Alaska:  Assessing the ocean climate hypothesis. Fisheries Oceanography 15. DOI: 10.1111/j.1365-2419.2006.00408.x

## Section II:

## Research Proposed for 2007

Projects proposed for 2007 consist of a continuation of several projects currently underway and four new projects. Continuing projects include:

- Project 413.00 - PIT tag recovery efforts will continue in 2007 with the scan sampling program. Scanning will also continue on the assessment survey vessels.  No other changes are planned for port coverage or duration of sampling. Planning for this activity is based on a March 1 – November 15 season.

- Project 620.00 – Sample analysis will continue in FY2007 in the otolith elemental fingerprinting (OEF) study. Laboratory analysis of accumulated samples will continue during 2007, including those collected in 2005 from southeast Alaska. A survey of potential index sites will begin in 2007.

- Project 621.00 - The study of the population genetic structure will continue in 2006 in two initiatives. In the first, sample testing and analysis is continuing to be conducted by Dr. Lorenz Hauser (UW Marine Molecular Biology Laboratory). A 2-year post doc approved by the Commissioners at the 2006 Annual Meeting fell through when the UW candidate took a job in the private sector. Additional samples were collected in 2006 on the summer surveys. The FY2007 budget will allow for the completion of the 2004 winter samples and begin work on the 2005 and 2006 summer collections.

- Project 622.00 - This set of PAT releases occurred in the summer of 2006 from assessment survey vessels in Areas 4A and 4D. Tags are scheduled to pop up in mid-February, 2007, providing additional information on summer to winter movements in the Bering Sea. FY2007 funding is for the satellite transmission fees from the pop-ups.

- Project 636.00 - The gonad staging/histology project will continue in 2007 with analysis of the 2004 samples and microscopy work. No additional sampling is scheduled. Work was set aside in 2006 as the researcher took a new position on the staff, which carried additional responsibilities.

- Project 646.00 - This set of PAT releases occurred in the summer of 2006 from assessment survey vessels in Areas 2A and 2B. Tags are scheduled to pop up in February-March, 2007, at 2-week intervals. These are expected to provide additional information on summer to winter movements within Areas 2A, 2B, and 2C. FY2007 funding is for the satellite transmission fees from the pop-ups.

- Staff will also continue with other long-standing projects in 2007. These include the collaborative work on contaminants with ADEC (#642.00), participation by IPHC staff on the NMFS trawl surveys (#604.00), data collections with water column profilers on the assessment surveys (#610.00), and the undergraduate internship program (#618). The otolith marginal increment analysis (#626.00) is expected to be completed in 2007. Finally, the investigation of sleeper shark population structure and development of an aging technique (#630.00) will focus on lab work and genetic testing of samples.

Four new projects are proposed for 2007 and briefly described below:

- Project 621.11 - In the second part of our genetics studies, winter charters will be conducted in three (and possibly four) areas to obtain additional tissue samples to address questions concerning the geographic separations observed in the 2005 winter samples, i.e., were the separations really generated by geographic differences, or by temporal variability in gene frequencies.

- Project 641.11 – This is a follow-up to the hook size/spacing work conducted in 2005, which took place in Area 3A. The results were actually confounded by the extremely high catch rates of halibut. It is likely that hook size or spacing effects were masked by the very high availability of halibut. It was our original intention that the Area 3A fishing would be contrasted with a Phase 2 experiment in an area of lower halibut density, which is planned for 2007 in Area 2B. Conducting this experiment in Canada would have the added element of dogfish competition for hooks.

- Project 651.00 – Recent research suggests that certain types of magnet or rare earth metals in proximity to baited hooks might help reduce the catch of unwanted sharks. We propose examining whether dogfish are similarly affected, initially in a controlled tank environment.

- Project 652.00 – Past derivation of setline selectivity has been from tag studies, and this project would involve actual underwater observations of halibut capture using the Didson sonar technology.

Projects conducted under contract to other agencies or through research grants will be continued in 2007. IPHC port sampling activities in Alaska will continue being augmented by a grant from NMFS (Project 375.00), and IPHC port samplers in Alaska will collect sablefish logbook data for the NMFS Auke Bay lab (Project 628.00).

We are also awaiting word on several grants which would enable several other projects. This includes: 1) a grant from PSMFC for a second year of additional survey stations off Washington; 2) funding from the State of Oregon for a similar set of additional stations off Oregon; 3) funding by ODFW for the purchase of a water column profiler dedicated for use on the Oregon portion of the Area 2A summer assessment survey; and 4) funding by NPRB for a study of electronic monitoring on halibut vessels off Alaska.

Funded Research

#### Project 413.00: 	PIT tagging study:  Fourth year of tag recovery and scanning

Start Date:  2003

Anticipated ending:  2008

Personnel:	J. Forsberg, C. Blood, G. Williams, B. Clark, A. Ranta, scan samplers

Scanning for PIT tags will continue in 2007. IPHC will hire samplers for Alaskan ports, while contracting with AMR for the Canadian ports and continuing to seek state and tribal assistance in Area 2A. Sampler duties include scanning commercial deliveries for PIT tags, and conducting regular tests of detection and piece (fish) counts to measure accuracy of sample data. Project costs are expected to be about the same as last year. Modest increases are expected in (a) salaries (cola), (b) our contract with AMR for sampling BC, and (c) retrofitting of the scanning equipment with improved hardware.

#### Project 416.00: 	PIT tagging study:  Double tagging experiment

Start Date:  2003

Anticipated ending:  2008

Personnel:	J. Forsberg, G. Williams

During September 2003 in Area 2B, 2,661 halibut were tagged with external wire spaghetti tags on the dark side of the head, and internal PIT tags. The purpose of the study is to examine the retention and durability of internal PIT tags in situ. When a halibut with this type of wire tag is turned in to IPHC personnel, the head is scanned to check for presence and operation of the internal PIT tag. A total of 586 fish have been recovered through the end of the 2006 commercial IQ season, including 157 during 2006. Proposed project costs in 2007 are for the rewards paid to the tag finders.

#### Project 604.00:	NMFS trawl survey:  At-sea data collection and IPHC data base management

Start Date:  1996

Anticipated ending:  Continuing

Personnel:  L. Sadorus, A. Ranta, B. Clark

A series of NMFS trawl survey data on halibut, parallel to our setline data, is extremely valuable to IPHC as a second fishery-independent data source for stock assessment. Trawl data are particularly useful because they include large numbers of juveniles (ages 3-7 yr) that do not appear in large numbers in the setline survey. Otoliths have been collected on the NMFS surveys since 1996 and provide relevant age information. These data are incorporated into a copy of the NMFS haul data, expanded to estimates of relative abundance and age/size composition by IPHC area (NMFS calculates estimates by INPFC area), and stored in a database at IPHC. Project cost is comprised of personnel and travel. In 2007, the staff is planning on placing two staff on the NMFS survey vessels.

#### Project 610.11:	Water column profiler project (annual survey project)

Start date:  2000

Anticipated ending:  Continuing

Personnel:  L. Sadorus, S. Hare, P. Stabeno (NMFS PMEL)

The IPHC maintains one of the most extensive sampling platforms in the north Pacific. This platform offers enormous potential for collection of valuable oceanographic data. In particular, understanding the dynamics of the structure of the mixed layer depth – a major GLOBEC goal - requires in situ vertical profiling. Use of this platform for oceanographic data collection capabilities not only would benefit the scientific community at large, but demonstration of sampling feasibility may also create other funding opportunities for collaborative research. In 2001 and 2002, the IPHC successfully deployed a SeaBird SBE-19 water column profiler from a commercial fishing vessel participating in the annual stock assessment survey. The profiler has been used on selected survey trips each season since. Project cost is directed towards annual maintenance of the one profiler owned by IPHC.

#### Project 618.00:	Undergraduate Internship

Start Date:  2002

Anticipated duration:  Continuing

Personnel:  L. Sadorus, T. Loher, other staff support as needed

One undergraduate will be selected through the intern/co-op programs at regional universities and colleges to do a combination of office and at-sea work based out of the Commission offices during the summer months. The program includes various pre-determined office tasks as well as being assigned a research project then designing and executing said project. A final report and presentation are given at the conclusion of the employment term.

#### Project 620.00:	Analysis of spatial recruitment dynamics in Pacific halibut using otolith elemental fingerprints (OEF):  Phase 2

Start Date:  2002

Anticipated Ending:  Continuing

Personnel:  T. Loher, S. Wischniowski, temporary staff

Results to-date using age-2 halibut from western Alaska suggest that otolith elemental signatures can be used to successfully distinguish and classify individuals within general geographic regions (Bering vs. Kodiak vs. Cook Inlet), with 80-90% accuracy. The addition of oxygen and carbon isotope ratios to the existing trace element data improved the model considerably. Work in FY 2007 will be comprised of site identification, and numerical analysis of age-1 (southeast Alaska) samples in order to examine issues of temporal stability in OEFs over time. In order to obtain ecologically meaningful results from this project, we will conduct coast-wide sampling of nursery habitats in a single summer to collect same-age fish (presumably age-1) with which to generate a coast-wide “OEF map”. We do not know whether all fish need to be collected within a brief window (weeks) or can be collected over a broader period (months). The answer depends upon whether drift at a site over short periods (within season) is substantial relative to regional differences. Second, we don’t know whether the signature identified in an area is unique to that area only in the year of capture, or will persist over time. For example, will Bering juveniles from a number of consecutive cohorts all demonstrate the same oxygen isotope signature, or is the signature year-specific? If the former, then a single OEF-map might characterize numerous cohorts. If not, it will be useful only for the cohort used to generate it. Second, we propose to begin the process of site establishment, as originally approved in our FY 2004 budget. We need to establish index sites in order to conduct coast-wide nursery sampling. The IPHC has no real experience with early juvenile work, so we have no established sites. Potential sites in BC and Yakutat will be assessed using a chartered vessel in 2007.

#### Project 621.00:	Genetic population structure of Pacific halibut assessed via nuclear microsatellite diversity – lab work by UW

Start:  2002

Anticipated Ending:  2007

Personnel:  T. Loher, L. Hauser (UW-MMBL), other staff as needed

Results from a preliminary population analysis of the summer 2002 samples suggested potential reproductive isolation in the Aleutians. Tissue samples were collected in winter 2004 to address the question of whether or not the Bering Sea is reproductively isolated from the Gulf. The analyses of these by Dr. Lorenz Hauser (UW - Marine Molecular Biology Laboratory) are nearing completion. His lab is also continuing with the testing and analysis of the summer samples from 2005 and 2006, and would also begin testing of samples from the following project.

#### Project 621.11:	Genetic population structure of Pacific halibut assessed via nuclear microsatellite diversity – collection of additional winter samples

Start:  2007

Anticipated Ending:  2007

Personnel:  T. Loher, L. Hauser (UW-MMBL), other staff as needed

A second winter survey is proposed based on the analysis of the 2004 winter samples, which suggested relative separation between the Bering and Gulf, relative to relatedness between Kodiak and Cape St. James. However, all separations were characterized by relatively low Fst values. Importantly, the Fst values are low enough that additional sampling is warranted. At issue is whether the separations observed in 2005 were really generated by geographic differences, or by temporal variability in gene frequencies. Do the gene frequencies drift so much that samples taken in a different year will generate different results?  In order to answer that question we need to re-sample the same sites.

#### Project 622.11:	PAT tagging:  summer 2006 releases (Areas 4A and 4D)

Start:  2006

Anticipated Ending:  2008

Personnel:  T. Loher

Electronic pop-up, satellite-transmitting archival tags (PATs) can record ambient temperature, depth, and light level (used to estimate longitude under certain conditions) while attached to fish. The tags are programmed to release from the fish on a pre-determined date, float to the surface, and emit a satellite signal that indicates the tag location and downloads all of the environmental data to the satellite. The result is a record of the fish’s final location, along with important environmental and behavioral data throughout the fish’s time at liberty.

During the 2006 summer setline survey, 24 PATs were deployed in the Bering Sea off the summer assessment survey, 12 in Area 4A and 12 in Area 4D. These tags were programmed to release from the fish and report their location and data during mid-February 2007. Costs for 2007 are for possible invoice for satellite transmission fees (these could be delayed into 2008) and potential reward costs. This set of releases was conducted with a grant from the North Pacific Research Board, with additional funding provided by APICDA and CBSFA.

#### Project 636.00:	Analysis of gonad staging on IPHC setline surveys

Start:  2004

Anticipated Ending:  2007

Personnel:  T. Geernaert, B. Leaman (other staff as needed)

The IPHC Stock Assessment surveys assess maturity of halibut based on visual criteria established in the early 1990’s and modified in 1995. These survey data combined with the age data are important components in the stock assessment model. Four maturity stages are presently assigned to female halibut; immature (F1), maturing (F2), spawning (F3) and resting (F4). Once a female halibut has spawned, the gonad transitions to a resting phase, back to maturing, and then to spawning again. Our criteria for classification also assume that the immature (F1) stage is only seen with immature fish but we are seeing anomalies during the survey that could question this assumption. Mature females are seen as small as legal size (82 cm) but, area-wide, there have been several large 100+ cm females whose gonadal characteristics classify them as immature (never spawned). The SSA survey data also suggest that fish in the southern latitudes (Area 2B) mature earlier and possibly spawn earlier that fish in the northern latitudes (Area 3A and west). The timing and duration of these events are not clearly understood. We would like to re-evaluate our classification criteria and examine the stages and gonadal tissue development more closely.

In 2003 preliminary histological work on the female gonads was initiated. We developed a sampling design and collection protocols for the 2004 surveys. In 2004, during winter and summer surveys, female gonads from three different regions, in each stage of development, were collected. Three different histological subsamples have been prepared and we are presently standardizing the sample sites on the gonad for the final slide preparation. We have collected nearly 240 gonad pairs and will be analyzing multiple sites from each sample in 2007.

#### Project 640.00:	PAT tagging:  summer 2005 releases (Areas 2B, 2C, and 3B)

Start Date:  2005

Anticipated ending:  2007

- Personnel:  T. Loher, sea samplers

This study is intended to investigate the preliminary observation that adult (presumably female) halibut tagged in the Gulf of Alaska at southeasterly and southwesterly locations (Areas 2B, 2C, and 3B) may have shorter residence times on their summer feeding grounds than fish found in Area 3A. In particular, Gulf PSAT data from 2002 suggest that southerly fish may begin their fall migration as early as September, as evidenced by an increase in depths visited, which may indicate movement away from their summer feeding locations to the shelf-break. We have no information regarding timing of the spring return-migration from the shelf-break back to shallower coastal waters.

In 2005, 26 fish in Areas 2B, 2C and 3B were tagged during the summer setline survey. Focusing primarily upon the eastern Gulf, 18 tags deployed at three general locations (lower Queen Charlotte Sound, northern Queen Charlottes, and western Baranof-Chichagof Islands). Four fish were tagged at each of two locations in Area 3B (Semidi and Sanak Islands). Tags are programmed to pop-up during the last week of May, 2006. Project costs for 2007 consist of the satellite time for transmission relay and potential tag rewards.

#### Project 641.11:	Hook spacing and size impacts on length selectivity and CPUE

Start:  2005

Anticipated ending:  2008

Personnel:  B. Leaman, S. Kaimmer, R. Webster, Survey team

The adoption of IQ management for halibut and sablefish, together with coincident seasons for these species, has resulted in an increased amount of mixed-target or combination fishing for both halibut and sablefish in Alaska. The optimum gear for the two species is quite different, with sablefish gear using smaller 13/0 or 14/0 hooks and short 36-48” spacing, while optimum gear for halibut may be larger 16/0 hooks with 15-18’ spacing. IPHC assessments make corrections for hook spacing relative to the IPHC standard 1800-ft 100-hook skate. However, the adjustment is based on a relationship developed in the 1970s from spacing experiments using J-hooks. No adjustment of CPUE for hook size is made. There is concern that smaller hooks may affect size selectivity, hence CPUE. This study will address potential differences in CPUE and size selectivity of selected combinations of hook size and spacing in the commercial fishery relative to the configuration of the standard IPHC survey skate.

Phase 1 of the study took place in the waters around Kodiak, AK, and experienced extremely high catch rates of halibut. It is likely that significant hook size or spacing effects are masked by the very high availability of halibut. It was our original intention that the Kodiak fishing would be contrasted with a Phase 2 experiment in an area of lower halibut density. Conducting this experiment in Canada would have the added element of dogfish competition for hooks.

#### Project 642.00:	Assessment of mercury and contaminants in Pacific halibut

Start Date:  2002

Anticipated ending:  Continuing

Personnel:  C. Dykstra, Alaska Department of Environmental Conservation (ADEC)

For the last few years, health officials and media have raised the profile of pollutant contamination in fish (methyl mercury, PCB’s, pesticides). Since 2002, the IPHC has been working collaboratively with the Alaska Department of Environmental Conservation (ADEC) to collect halibut tissue samples to be analyzed for heavy metal and organic pollutant loading. The principal results from the 2002 collection led the Alaska Division of Public Health in 2003 to conclude that the concentrations of heavy metals in Alaskan Pacific halibut are not a public health concern. In 2004 the first results regarding organic pollutants (PCB’s, pesticides) were released demonstrating that halibut had the lowest concentrations of the five species (including salmon and sablefish) examined. Since 2002 the IPHC has submitted 572 samples for testing by ADEC. The mean level of total mercury for these samples has been 0.352 ppm (for comparison the FDA limit of concern for methyl mercury is 1.000 ppm, the EPA and the CFIA level of concern is 0.500 ppm) ranging from non-detectable to 1.947 ppm. The IPHC and ADEC are continuing to qualify the data with physical parameters (age, size, and weight) and additional analyses will be done on the samples. ADEC and EPA planned on going ahead with this study regardless of IPHC input. Our involvement in the project has allowed us to provide input on study design, sampling protocols in the field, etc., which will make the resultant information much more robust.

Sampling continued in 2006 with a targeted collection of 60 samples (30 from fish weighing between 20 – 40 lbs. and 30 from fish weighing between 40 – 100 lbs.) from each of four regions (Sitka, Prince William Sound, Area 4A Edge, and St. Paul) during the setline survey. Results will be published as they become available. ADEC has expressed interest in further assessments of contaminant occurrence in halibut in 2007.

#### Project 646.11:	PAT tagging:  summer 2006 releases (Area 2A)

#### Project 646.12:	PAT tagging:  summer 2006 releases (Area 2B)

Start Date:  2006

Anticipated ending:  2008

Personnel:  T. Loher, C. Blood, B. Clark

The purpose of this study is to identify summer-to-winter seasonal movements of halibut in Areas 2A and 2B. In 2006, 18 and 54 PAT tags were released from the Area 2A and 2B summer assessment surveys, respectively. The tags are scheduled to pop-up in February-March, 2007, at two week intervals. Costs for 2007 are for possible invoice for satellite transmission fees (these could be delayed into 2008) and potential reward costs.

#### Project 650.00:	Archival tagging – pilot studies

Start Date:  2006

Anticipated ending:  Continuing

Personnel:  T. Loher

This study represents a controlled test of the relative utility of three different models of internal archival tag that can be used on relatively small (60-99 cm) halibut. The 24 halibut being held at the Oregon Coast Aquarium in Newport were successfully tagged with one of three types of archival tags. The fish will be held until early 2007 in order to monitor their recovery and rate of incision closure. They will then be sacrificed and examined internally to assess any potential reactions to the internal tag, and to determine the feasibility of non-invasive sex determination via veterinary ultrasound. Having perfected the surgical techniques and determined the best tag configuration, deployment of internal archival tags on wild fish could begin as early as the 2008 setline survey.

#### Project 651.00:	Effects of magnets and rare metals on the catch rates of spiny dogfish

Start Date:  2007

Anticipated ending:  Continuing

Personnel:  S. Kaimmer

Unwanted or prohibited bycatch in longline catches is a problem in both our research and the commercial fishing for halibut. Recent research suggests that certain types of magnet or rare earth metals in proximity to baited hooks might help reduce the catch of unwanted sharks. This likely also includes dogfish (Squalus acanthias). In 2006, a New Jersey company, Shark Defense, won the Smart Gear award for a demonstration where magnets reduced shark catch on floating longlines. They have gone on to demonstrate similar results with rare earth metals. We are proposing a pilot study to investigate in vitro fish responses to these magnets or metals. This initial study will look at responses of captive dogfish to baited hooks in the presence and absence of these magnets or rare earth metals. This project will use structured observations of dogfish feeding behavior to determine effects of either the magnets or the ‘mystery metal’. This will be done at a fish holding facility, possibly the UW lab in Friday Harbor, or the NMFS lab in Manchester.

#### Project 652.00:	Verification of setline selectivity using Didson sonar

Start Date:  2007

Anticipated ending:  Continuing

Personnel:  S. Kaimmer, B. Clark

The purpose of the study is to verify, by direct observation, the halibut hooking success curve for halibut on setlines. This curve has been estimated from tag release/recovery data and from a small set of direct observation data collected with an underwater video camera in shallow waters. This project would generate a larger set of observations and operate in more appropriate depths. The study would use leased DIDSON (dual frequency identification sonar) sonar, and a gear frame which was constructed in 2006 for the Didson trap experiment. Although we expect the DIDSON to detect many more hooking attacks than previous methods, this study will be the first real test of this approach, and as such is exploratory in nature. It is possible that additional data will need to be collected in future work in order to precisely estimate hooking success for the full range of 5-cm length classes.

#### Project 653.00:	Species identification of amphipods frequenting Pacific halibut

Start Date:  2006

Anticipated ending:  Continuing

Personnel:  B. Leaman, E. Soderlund

The project intends to document the occurrence and virulence of attacks by predatory amphipods on halibut caught on IPHC surveys and, by inference, the commercial fishery. The commercial industry suffers annual losses of product due to amphipod predation and must adjust its fishing locations and practices in response to predation. Harvester discussions indicate that predation sites are both known and ephemeral, and the virulence may vary interannually at a given site. The specific identity of the amphipods has not been established and it is probable that more than one species is involved. Harvesters are interested in both documentation of predation areas for avoidance, as well as gaining an understanding of the dynamics of the species at given sites, i.e., are there cycles of abundance that respond to other factors. Data were collected on all stations during the 2004, 2005, and 2006 stock assessment surveys as part of standard protocol, recording incidence of sand flea predation, and the extent and virulence of the predation. The 2006 was the last year of data collection for this stage of the project. No additional analytical work on this project was completed in 2006, due to other commitments of the principal investigator.

Other 2007 Research – Contracts and Grants

#### Project 375.00:	Alaska port sampling

Start Date:  2002

Anticipated ending:  Continuing

Granting agency:  NMFS

Personnel:  H. Gilroy, M. Larsen, L. Hutton

The commercial fishery port sampling program hires samplers to collect otoliths, halibut lengths, fishing logbook information and landed weight data. The U.S. program includes staffing eight Alaskan ports and Bellingham, Washington. The samplers act as the liaison between the fishing industry and the Commission staff in Seattle. The Commission is responsible for the overall assessment and management of the halibut fishery and the data collected are necessary for stock assessment. The U.S. Government adopted the Individual Fishing Quota (IFQ) allocation program in 1995. This grant provides funds to the IPHC for the incremental cost to the Commission sampling program due to the IFQ program. The grant is generated from the NMFS IFQ Fee Collection Program.

#### Project 628.00:	Alaska catcher vessel logbook and sablefish data collection

Start Date:  1999

Anticipated ending:  Continuing

Granting agency:  NMFS

Personnel:  L. Hutton, H. Gilroy, A. Taheri, port samplers

IPHC and NMFS Auke Bay Lab (ABL) have a sablefish data collection program. The program was reviewed and modified in 2003/2004 to meet the IPHC confidentiality policy and to encompass all vessels rather than just vessels greater than 60 feet. Under a Statement of Work, NMFS contracted IPHC staff to interview the IFQ fishers to review and collect the sablefish information in addition to the halibut information. Data are entered by IPHC staff with an electronic summary provided to the NMFS ABL scientists. In the summarized data, the vessels are assigned a unique code to preserve confidentiality.

Pending Grants for Other 2007 Projects

We are awaiting approval on several grants which would enable several other projects. This includes: 1) a grant from PSMFC for a second year of additional survey stations off Washington; 2) funding from ODFW for a similar set of additional stations off Oregon; 3) funding by NPRB for a study of electronic monitoring on halibut vessels off Alaska; and 4) funding from the State of Oregon for the purchase of a water column profiler for dedicated use on the Oregon portion of the Area 2A assessment survey.

Research Conducted Without Direct Funding

#### The 2007 stock assessment

Personnel:  B. Clark, S. Hare

The annual stock assessment process comprises a large amount of work including preparation of IPHC data, estimation of bycatch by length in other fisheries, model development and validation, model fitting, examination of residuals, comparison of alternative model specifications, sensitivity tests, evaluation of harvest strategy, incidental analyses, and reporting.

#### Development of IPHC harvest policy

Personnel:  S. Hare, B. Clark

Staff quota recommendations are calculated by applying a judiciously chosen harvest rate to an estimate of present exploitable biomass. The constant harvest rate policy was developed on the basis of its performance over a long time horizon and with the explicit goal of avoiding reaching the minimum stock sizes seen in the 1930s and 1970s. In 2003 the staff proposed a conditional constant catch policy under which total removals would be capped at a chosen ceiling level at high biomass levels, while a constant harvest rate policy would continue to be employed at low and intermediate stock levels. The Commission did not adopt the proposed policy at the 2004 annual meeting, and a staff/industry workshop on harvest policy alternatives in September 2004 showed general satisfaction with the present policy, as mediated in practice by the judgment exercised by the Director in developing staff recommendations and by the Commission in finally setting catch limits. In 2004, an explicit lower limit on spawning biomass and a threshold below which the harvest rate will be reduced—were added to the constant harvest rate policy. As a result the target constant harvest rate for the core IPHC areas (2B, 2C, and 3A) was lowered to 22.5% from 25%. The staff will continue to evaluate the constant harvest rate policy. In particular, we will recalculate the optimum harvest rate itself in light of our present understanding of stock dynamics and new information on commercial length-specific selectivity coming from the PIT tag experiment.

#### Development of a robust management procedure

Personnel:  B. Clark, S. Hare, B. Leaman

Staff catch limit recommendations are derived from the annual stock assessment by applying a constant harvest rate to the estimates of exploitable biomass, in the belief that the assessment model is correctly specified and the estimates are accurate. In fact there are a number of structural uncertainties about the model, and the assessment itself has become highly complicated, so it is vulnerable to any small error in data compilation or programming. The aim of this project is to develop a procedure for deriving catch limit recommendations that would achieve the desired harvest policy, potentially relying on much simpler calculations and at the same time be effective across a range of uncertainties about stock, fishery and management behavior. Such procedures have been developed for other fisheries and it is appropriate to investigate their application to halibut management.

#### Estimation of halibut abundance from mark-recapture data

Personnel:  R. Webster, B. Clark, B. Leaman

The IPHC has conducted many tagging programs since the 1920s. IPHC has also conducted at least five reviews of these programs, again with differing objectives. However, many of these reviews did not account for the issues of non-reporting or differential reporting of tags by areas, fishing effort effects on recovery probabilities, the relationship of initial tag releases and the density of fish in given areas, and the effect of seasonal migratory patterns on the analysis of recoveries were not always considered. A changed paradigm for the area-specific impacts of juvenile bycatch, questions concerning the effects of changing seasonal distribution of fishing effort, potential halibut distribution changes with climatic shifts, and the utility of juvenile surveys in specific areas have all prompted concerns about halibut movements.

The staff marked the catch of three skates at each survey station coastwide in 2003 and in Areas 2B and 3A in 2004. Preliminary analysis of the 2004 recoveries showed good agreement with the stock assessment in Areas 2B and 2C, but farther west the mark-recapture estimates were much higher than the assessment estimates. Recoveries in 2005 followed a similar pattern. The 2006 recoveries will be added to the analysis this year.

#### Seabird occurrence project

Cost: Staff salaries

Start Date: 2002

Anticipated ending: Continuing

Personnel:  T. Geernaert, Washington State Sea Grant

During the 2004 stock assessment surveys, sea samplers counted the number of seabirds in the vicinity of the vessels following gear retrieval. This is the third year the seabird occurrence data were collected on IPHC surveys. Sampling after the haul addresses the question of where and when certain seabird species occur. Ultimately, these data might be used to identify appropriate seabird deterrent requirements in certain geographic locations, especially for the halibut fleet. IPHC has developed a database to store seabird occurrence data from the IPHC stock assessment surveys, as well as the NMFS and ADF&G sablefish surveys. The data are currently being analyzed. IPHC, in coordination with Washington Sea Grant, will be writing a joint paper on the results for the 2002-2004 data. The collection project is ongoing.

#### Seabird data repository (Project 643)

Start Date:  2005

Anticipated ending:  Continuing

Personnel:  T. Geernaert

This project encompasses the storage by IPHC of various types of seabird data collected on agency surveys, including the seabird occurrence project conducted on the assessment surveys. Although IPHC has been collecting these data on its assessment survey since 2002, other agencies are just beginning the same procedure. IPHC’s head-start with these types of data led other programs to seek the efficiencies provided by IPHC in data management for optimal use by analysts and managers. A grant from Washington Sea Grant funded this activity in previous years.

#### Estimates of bycatch on the setline surveys

Start Date:  2003

Anticipated ending:  Continuing

Personnel:  C. Dykstra, Survey Team, and DFO personnel

Area 2B

Rockfish bycatch in the halibut fishery can be a constraint in conducting halibut fishing in some areas. In 2006, IPHC worked with DFO to allow a third biologist on IPHC survey vessels to sample rockfish. The program was funded by industry (Pacific Halibut Management Authority). Data collected included hook by hook occupancy information, otoliths, maturities, and lengths for rockfish and sablefish. This is the fourth year of the extensive bycatch sampling program in Canada, and continued collaboration is anticipated.

Area 2A

Since 2002, the IPHC has worked cooperatively with both the Washington Department of Fish and Wildlife (WDFW) and Oregon Department of Fish and Wildlife (ODFW) to collect rockfish bycatch data. All rockfish caught on operations in 2A are tagged with an external Floy tag and the tag number is recorded with the set (and recently the skate number) information. At the offload, a state biologist meets the vessel and samples the rockfish (length, weight, maturity, genetic sample, and otolith). The IPHC then provides each agency with the effort information collected as part of the normal survey data collection.

In 2006, IPHC and Washington Department of Fisheries received funding from PSMFC to connect a joint project with industry. The Area 2A IPHC charter was expanded to included 25 special stations in the Washington survey region to look at rockfish populations. Station locations where selected by WDFW in an effort to better characterize rockfish abundance. Stations were selected with the hope of targeting more rocky bottom than the standard survey stations in the Washington region. Three skates of gear where fished at each station as a precautionary approach due to the exploratory nature of these stations and concerns of over fishing yelloweye rockfish. Activities at each station were identical to those on standard IPHC stations, and rockfish were handled as described above. A summary of this project will be submitted to PSMFC by the end of November 2006. Depending on those results, there may be a second season of sampling under this funding opportunity, although station positions may be changed to better characterize rocky bottom type.

#### Sleeper shark investigations (Project 630)

Start Date:  2003

Anticipated ending:  Continuing

Personnel:  S. Wischniowski, G. Williams

Ageing Study

The Pacific sleeper shark (Somniosus pacificus) age determination program commenced in 2005. Selected samples were cleaned of extraneous meat and connective tissues and sliced into 5mm thin-sections. It soon became evident that difficulties in the pre-staining preparation phase were going to be encountered. Pacific sleeper sharks lack a great deal of calcification to their vertebra, this structure can best be described as a “cartilagic garden hose”. The entire vertebra is almost completely composed of cartilage, and lacks any hardened surfaces including the centra (structure typically utilized to age sharks). These centra can best be described as thin membranes similar to the tympanic membrane of the inner ear in mammals. As fragile as this structure is, it more than likely does not function as the site of articulation as in most vertebrates. It is surmised that these centra might function as a means of regulating and controlling spinal fluid pressure within the vertebra. Specimen “A” (our first test sample) was recorded to have ~ 75 ml of spinal fluid in-between its two centra. It is possible the animal might gain structural support by retaining a turgid environment within its vertebra.

Further difficulties were encountered when the centra was removed and dried. Water loss resulted in a large amount of shrinkage and cracking which prevented further manipulation of this structure. Current experiments are ongoing to determine which methodology works best to retain hydration of the structure prior to staining. Both EtOH and glycerin (without thymol) are currently being investigated.

Genetics Study

The objective of the second component of this research into Pacific sleeper sharks is to determine if these sharks come from a homogenetic population. The population dynamics of sleeper sharks within the northeast Pacific is not well documented. Preliminary tagging studies have indicated that at least some sleeper sharks display a resident behaviour, and likely have relatively small home ranges. To test this assumption tissue samples were collected from live sharks by way of biopsy darting during the 2004 Stock Assessment Survey. A simple test of homogeneity will compare samples collected from regions of high occurrence to peripheral regions of lesser occurrence. All tissue samples for this project have been collected, and no further are need for this experiment. This portion of the research proposal will specifically target the analysis aspect of the study.

Mitochondrial DNA polymorphisms will be used as the initial genetic marker system to investigate population differentiation among the three sampling locations. We will initially attempt amplification using primers located within the proline tRNA and 12S rRNA regions of the mitochondria. These primers have been used to examine population genetic structure across a similar geographic range in blacktip sharks and yielded sufficient information to differentiate among nurseries of this species. Statistical analysis will be by way of X2 and AMOVA probabilities of haplotype homogeneity across sampling sites. The lab portion of this experiment will commence in the fall of 2007.

#### Review of port sampling, 1994 to present

Start Date:  2002 (Deferred in 2004)

Anticipated ending:  2007

Personnel:  L. Hutton, T. Kong

Report on the changes that have occurred in the commercial catch sampling and port sampling program from 1994 to the present. For example, the report will review the changes made to the program due to the implementation of the IFQ fishery in Alaska, the changes in the method of logbook data collection in the U.S., as well as changes in the Canadian program. This is an update of Technical Report 32.

#### Electronic reporting project for commercial landings in Alaska

Start Date:  2002

Anticipated ending:  Continuing

Personnel:  H. Gilroy, L. Hutton, T. Kong, A. Tesfatsion, H. Tran

IPHC, ADF&G, and NMFS staffs have worked with contractors initially hired by Pacific States Marine Fisheries Commission (PSMFC) to implement a cooperative interagency electronic fishery reporting system for commercial landing records in Alaska. The project included designing a web based Interagency Electronic Reporting System (IERS) with the repository database in the State Office Building in Juneau. In May 2006, IERS was optional for statewide groundfish landings and IFQ/CDQ halibut and sablefish. Since the program is operational 24/7 the agencies are working with an outside company to provide help desk support during non-business hours. For halibut, the system reduces duplicative reporting resulting from the current requirements of completing ADF&G fish tickets and NMFS RAM quota share reports. The application (eLandings) records data elements required by regulations, prints fish tickets, and connects with the NMFS quota share database. The appropriate data from IERS is being sent to the agencies for their internal databases. The application allows processors to import or export data into their own databases so double entry is not necessary. The project is ongoing and industry personnel and agency staff have provided feedback on the operation so the application will continuously be modified to add additional features. In 2007, additional fisheries will be added including statewide shellfish.