# IPHC Research Program:

# Review of 2007 Projects and Proposals for 2008

The International Pacific Halibut Commission Staff

## Introduction

This document reviews research conducted by the IPHC staff in the past year and proposed for the upcoming year. The report is divided into two sections, with the first section reviewing the status of research projects conducted 2007. The second section presents the preliminary staff research proposals for 2008. Information is provided on when each project was initiated, the anticipated completion date, the annual cost, a description of the costs, and the purpose of the project. This report does not include ongoing staff tasks such as data collection and processing that are necessary for the management of the fishery.

Research projects are organized into three funding categories that reflect availability and source of research funds. Limited research requiring direct financial support from the Commission is possible under the basic $3.797 million (as of 2007) government appropriations, although a number of programs can be conducted using only the staff resources that are supported by the appropriations. The three funding categories are:

- Funded Research: Necessary research projects of high priority that can only be conducted with revenues generated by survey fishing in 2007, and/or carry-over from 2006;

- Contracts and Grants: Agreements with other parties to conduct specific research. In this case, contracts and grants are shown for projects where the IPHC staff is the principle investigator; and

- Research conducted without direct funding: Necessary research projects of high priority that can be conducted within the IPHC budget.

Nearly all of the research done by the staff is directed toward one of three continuing objectives of the Commission:

i) Improving the annual stock assessment and quota recommendations;

ii) Developing information on current management issues; and

iii) Adding to knowledge of the biology and life history of halibut.

In each of these areas our routine work program applies the best information and methods available, and our research program aims to improve the information and methods by answering the most important outstanding questions.

## SECTION I:

## REVIEW OF RESEARCH CONDUCTED IN 2007

Research conducted by the IPHC staff during 2007 continued in three basic areas:  life history, fish movements, and general biology. Most of the projects were conducted as part of the normal staff duties, with no additional funding required outside of staff salaries. Funding for projects outside of staff salaries came from supplemental funding, and these projects are outlined below.

## 2007 Research Highlights

The PIT tag dockside detection program by scan samplers continued in 2007, with samplers in eight Alaskan and four B.C. ports. Additionally, IPHC received state and tribal assistance in scanning in nine ports in Washington and Oregon. Through 21 October, almost 24 million pounds (41% of total landings) have been scanned. The number of tags recovered in 2007 totals 276 from the 2003 primary experiment, 182 from the 2004 releases, and 59 from the September 2003 double tag experiment (releases totaled 2,662). The latter project was conducted to confirm the PIT tag shedding rates observed during earlier holding experiments in Seward. The recovery rate for this experiment is now 24%. Of the 59 double-tagged fish recovered in 2007, no PIT tags were missing from heads with wire tags attached and in six recoveries, the wire tag had shed and only the PIT tag was found by scan samplers.

The Otolith Elemental Fingerprint (OEF) project (#620) has shown that, using age-2 halibut from western Alaska, the chemical composition of otoliths can be used to successfully distinguish and classify individuals within general geographic regions (Bering vs. Kodiak vs. Cook Inlet), with 80-90% accuracy. The spatial model developed over the last two years relies primarily upon oxygen and carbon isotope ratios and secondarily upon trace element data, thus completing the first phase of the project which was simply a proof of concept. During 2007, field effort was expended in Area 2B to locate juvenile nursery areas. A number of sites (east Cape Scott, north Hope Island, Goose Island Banks, Oval Bank, McIntyre Bay, Virago Sound) failed to produce early juvenile halibut, but age-0 and age-1 halibut were captured at three sites describing the length of Dogfish Banks, at Rose Point, Cape Ball, and Sandspit. This represented successful establishment and mapping of nursery research sites in Canadian waters, as well as establishing a southern range extension for Pacific halibut nursery grounds. After evaluating the results and potential for further resolution of stock identity in this project, the Commission’s internal research review committee decided to stop any additional work on this project. The primary reasons were the inherent limitations of the equipment used to detect the elements, and although aimed at different life-history stages, the desire to pursue other means of establishing stock identity (e.g., genetic) which have greater potential for success.

Effort on the Genetics project (#621) continued in 2007 on two fronts. The first consisted of three vessel operations in February 2007 which collected tissue samples from spawning fish in the Queen Charlotte Islands (Area 2B), Portlock Bank (Area 3A), and Pribilof Canyon (Area 4). The sites were fished essentially simultaneously and produced genetic samples from 698 adult halibut. Subsequent additional time was provided by the vessel conducting the Area 4 work to collect additional samples from grounds north of Adak Island. These samples will be added to the present microsatellite analysis; other samples will be reserved for use in future work employing potentially more powerful markers such as single nucleotide polymorphisms (SNPs), expressed sequence tags (ESTs), and mitochondrial DNA (mtDNA).

The second component of the 2007 genetics studies was continued sample analysis under the supervision of Dr. Lorenz Hauser at the University of Washington’s Marine Molecular Biology Laboratory. This lab work moves the present analysis closer to completion before we move on to potentially more promising markers. Our technician is presently “filling gaps” in the existing dataset (i.e., re-running samples from fish that did not properly amplify properly on the first analysis) and will also add a sixth site (Adak Island) to the analysis. Preliminary research using summer-collected samples (see IPHC Scientific Report #81) suggested greater isolation in the Aleutian Islands than elsewhere, and we now have samples from spawning season that will allow us to test this result more rigorously.

In 2007, two PAT tag experiments (#646.11 and #646.12) were scheduled to pop-up. The tags were put out during the 2006 setline survey:  18 fish tagged in Area 2A; 60 in Area 2B. The tags were programmed to release on one of three dates: February 1, February 15, or March 1, 2007. The study was designed primarily to answer questions regarding the relative amount of out-of-area interception likely to occur on alternative season opening dates. Fifty-six tags functioned as programmed and reported on their pop-up dates:  twelve of the 2A releases and 44 from 2B. In addition, one of the premature releases from the Area 2A tagging reported its position on January 18, and could therefore be included in the 2A emigration estimate. From the Area 2A releases, a total of five fish (total emigration rate = 39%) emigrated northward; four had moved to 2B and one to northern Area 2C. There was no apparent difference in emigration rate by date. From the 2B releases, a total of three fish (total emigration rate = 7%) emigrated northward. These fish were all located in Area 2C at pop-up: one at Cape Ommaney on February 1, one in Clarence Strait on February 15, and one in northern Dixon Entrance on March 1. These results differed from analyses from earlier conventional tagging that suggested a much higher proportion of the fish might be found out-of-Area on the specified dates. Differences may have resulted from having tagging larger fish in the PAT study than in conventional tagging work, a change in behavior in the period between the studies, the relative seasonal timing of present and previous studies, or fishery recapture biases in conventional tagging that are absent in PAT studies. It should be recalled that the previous studies generally tagged fish in winter and subsequently recovered them on the summer feeding areas. We do not know, for example, whether fish tagged in Area 2C and subsequently recovered in Area 2B had moved from Area 2B to Area 2C in the autumn prior to tagging, or had been 2C residents up until being tagged and moved to 2B prior to final capture as part of their lifetime west-to-east migration. The seasonal timing of the PAT tag study eliminates this confusion. The light-based location data from PAT tags also provides at least the potential to examine seasonal movements in their entirety by generating additional winter locations to ascertain whether the fish emigrated westward and returned by the Pop-up date. It should be noted, however, that technical limitations make it unlikely to make such assessments for the eastern stock component.

A second PAT tag study had tags pop up in 2007. This study (#622) looked to see if halibut which reside in the Bering Sea during summer are likely to move to the Gulf of Alaska to spawn, or instead remain in the Bering Sea. Joint funding received from the Central Bering Sea Fishermen’s Association (CBSFA), Aleutian Pribilof Island Corporation (APICDA) and the North Pacific Research Board (NPRB) allowed us to deploy PAT tags on 24 fish at two sites in the eastern Bering Sea during the 2006 survey:  twelve in Bering Canyon just north of Unimak Pass (4A), and twelve at Middle Canyon on the 4D Edge. Eight tags functioned properly from the 4D Edge release:  seven of these fish were located close to their release locations on the pop-up date, and one had moved south into the Bering Canyon. Ten tags functioned properly from the 4A release:  nine of these fish were located close to their release locations on the pop-up date, and one had moved eastward. The results are similar to former Bering Sea tagging in that they fail to support the hypothesis that halibut resident in the Bering Sea in summer move into the Gulf of Alaska (GOA) to spawn or contribute to GOA larval pools. In total, the Bering tagging experiment has generated winter locations for 42 adult halibut; all locations have been within the Bering Sea.

The pilot study (Project 650) on use of internal archival tags in halibut which began in 2006 continued in 2007. This pilot work represents a controlled test of the relative utility of three different models of internal archival tag that can be used on relatively small (60-99 cm) halibut. Since August 2006, 24 halibut ranging from 65-90 cm have been held in tanks at the Oregon Coast Aquarium in Newport. Three different tag varieties were tested on the fish: 1) Lotek LTD 1110, an 11 mm by 32 mm resin-body tag; 2) Lotek LTD 2310, a 16 mm by 76 mm silicon-coated stainless steel tag with a 24 cm external light stalk; and 3) Wildlife Computer MK9, a 17 mm by 67 mm resin-body tag with a 19 cm external light stalk. All tag varieties record temperature and depth, and the tags with light stalks are capable of recording ambient light for the purpose of estimating fish location. The one-year holding period has just concluded and fish will be sacrificed during the first week of December. They will be examined internally to assess any potential reactions to the internal tag, and we will also use this opportunity to determine the feasibility of non-invasive sex determination via veterinary ultrasound, so that future tagging can be conducted in a sex-specific manner. Follow-up work is being proposed for 2008 using this technology.

2007 also saw phase 2 of the hook size/spacing study (#641.11). Previous work in 2005 was conducted off Kodiak. In that study, catch rate by weight was an increasing non-linear function of hook spacing but no significant effect of hook size on catch rate was found. Hook size did have an effect on catch in terms of numbers of fish, with smaller hook sizes catching larger numbers of smaller fish. However, the 2005 Kodiak study experienced extremely high catch rates of halibut, and it is likely that significant hook size or spacing effects are masked by the very high availability of halibut. It was originally planned that the Kodiak fishing would be contrasted with a phase 2 experiment in an area of lower halibut density, such as in Canadian waters. Conducting this experiment off BC would have the added element of dogfish competition for hooks. However, recent Canadian court decisions pushed the 2007 experiment into Area 2C, where it was conducted in late July and early August. The data seem to be behaving better than during the 2005 experiment, and this is likely due to the lower density of halibut on the chosen fishing grounds. The CPUE of legal-sized halibut increased with increasing hook spacing, and generally increased with hook size. There is no clear relationship between the catch of sublegals and hook spacing, although sublegal catch does seem to be higher on the smaller hooks. The analysis will be completed in 2008.

IPHC has been involved in several cooperative studies which utilize the summer assessment survey and the catch of non-halibut species. Since 2002, the IPHC has worked cooperatively with both the Washington Department of Fish and Wildlife (WDFW) and Oregon Department of Fish and Wildlife (ODFW) to collect rockfish bycatch data. In 2007, IPHC and Washington Department of Fisheries received funding from Pacific States Marine Fish Commission (PSMFC) for the second year of a joint project with industry. The Washington survey region was expanded to include 18 special stations (ten of which where fished in 2006, and eight were new locations for 2007) to look at rockfish populations. Stations were selected by WDFW with the hope of targeting rockier bottom than traditionally fished by the standard survey stations in the Washington region, so as to better characterize rockfish abundance. Three skates of gear where fished at each station as a precautionary approach due to the exploratory nature of these stations and concerns for over fishing yelloweye rockfish. Activities at each station were identical to those on standard IPHC stations, and rockfish were handled as described above. A summary of this project will be submitted to PSMFC by the end of November 2007. Depending on those results, there may be a third season of sampling under this funding opportunity.

In 2007, IPHC worked with DFO to provide a third biologist on IPHC survey vessels to sample rockfish. While this is the fifth year of the extensive bycatch sampling program in Canada, it is the first year that the IPHC trained and deployed the third biologist (previous years the third was provided by Archipelago Marine Research Ltd.). The program was funded by industry (Pacific Halibut Management Authority). Data collected included hook by hook occupancy information for all species, and otoliths, maturities, and lengths for rockfish. Continued collaboration is anticipated.

In 2007, IPHC worked cooperatively with Alaska Department of Fish and Game (ADFG) to collect rockfish bycatch data. Rockfish caught in the Ketchikan, Ommaney, Sitka, Fairweather and Yakutat charter regions were marked with an external Floy tag and the tag number was recorded with the set and skate capture information. All marked fish were retained for sale. At the offload, state biologists (contract biologist for BC landings) would meet the vessel and sample the rockfish for length, weight, maturity, and the otolith. The IPHC then provides each agency with effort information collected as part of the normal survey data collection. This was a developmental year for this sampling effort and it evolved somewhat over the course of the season. As not all offloads were met by biologists, the IPHC samplers assisted with the data collection where possible. Additionally the work focused on demersal shelf rockfish (DSR), with the subsampling being constrained to those species. The IPHC did collect piece count observations for all rockfish involved despite the focus on DSR specimens.

The IPHC collected retention/non-retention information on Pacific cod for landings coming into Dutch Harbor and St. Paul. Survey vessels recorded the number and pounds of Pacific cod retained and discarded by survey station. This information was collected when the vessel initiated retention of Pacific cod, i.e., usually four days prior to the expected landing date. Additional subsamples from the retained Pacific cod were obtained opportunistically from the survey offloads by IPHC port sampling staff. This included piece count information and length data. This was part of a developing effort to collect bycatch information on Pacific cod in the western regions of our survey, where it makes up the largest component of our survey bycatch.

IPHC contracted with Dr. Al Stoner of the NMFS lab in Newport, Oregon to conduct lab trials observing halibut and spiny dogfish behavior in the presence and absence of magnets and mischmetals (#651). Dr Stoner found a significant decrease in dogfish attacks with the mischmetal but no effect on halibut behavior. A report from this study is currently in press. Field testing occurred in the summer of 2007 in Kachemak Bay, near Homer. In fishing trials, dogfish catches were reduced by about 15% using the mischmetal. However, neither the field trials nor the tank tests showed any significant effect on halibut catches.

A study to verify, by direct observation, the halibut hooking success curve for halibut on setlines took place in 2007 (#652). This curve has been estimated previously from tag release/recovery data and from a small set of direct observation data previously collected with an underwater video camera in shallow waters. The 2007 study leased a Didson (dual frequency identification sonar) sonar, and used a gear frame which was constructed in 2006 for the trap experiment. During a 10-day experiment out of Seward, 67 deployments of the Didson gear were made which witnessed over 50 halibut captures. The video data are expected to provide strong preliminary data to describe the halibut selectivity curve. The video files will be fully analyzed over this winter. Additional work is under consideration for 2008.

Finally, IPHC hired one intern (Project 618) in 2007. Ms. Kirsten Baltz (University of Alaska Fairbanks) worked May-August on a project titled “A spatial analysis of amphipod predation on longline-caught Pacific halibut”, which gave her an opportunity to spend time on a survey vessel collecting data. She presented his results to the staff, and her final report will be included in the 2007 RARA.

## 2007 Contract Research

NMFS Auke Bay Lab (ABL) has had a sablefish data collection program for several years and IPHC has assisted NMFS with the program. In 2003/2004, the program was reviewed and modified to meet the IPHC confidentiality policy and to encompass all vessels rather than just vessels greater than 60 feet. Under a Statement of Work (SOW), NMFS contracts IPHC to collect and review information on sablefish catches (Project 628) during the IPHC port sampler’s logbook interview. Sablefish data are entered by IPHC staff, edited, and an electronic summary provided to the ABL scientists. Vessels are assigned a unique code in the summarized data to preserve confidentiality. The SOW was renewed for 2007.

IPHC also received a grant from NMFS for the incremental increase in port sampling costs due to the IFQ program (Project 375). An application to ODFW for a grant to assist in the purchase of a water column profiler was approved in 2007. The grant, in the amount of $23,348, enabled data to be collected from the summer assessment survey vessel while operating in the Oregon survey region in 2007. Finally, a grant from NMFS was used to offset vessel charter costs during the field tests of mischmetal (Project 651). The grant was awarded through the agency’s emphasis on reducing bycatch.

# 2007 Research Publications

IPHC staff noted in Bold type.

Ames, R.T., Leaman, B.M., and Ames, K.L. 2007. Evaluation of video technology for monitoring of multispecies longline catches. N. Am. J. Fish. Mgmt. 27: 955-964.

Loher, T. In Press. Investigating variability in catch rates of halibut (Hippoglossus stenolepis) in the Pribilof Islands:  Is temperature important? Deep Sea Research II.

Seitz, A.C., Loher, T., and Nielsen, J.L. 2007. Seasonal movements and environmental conditions experienced by Pacific halibut in the Bering Sea, examined by pop-up satellite tags. Int. Pac. Halibut Comm. Sci. Rep. 84. 24 p.

Trites, A.W., A.J. Miller, H.D.g. Maschner, M.A. Alexander, S.J. Bograd, J.A. Calder, A. Capotondi, K.O. Coyle, E. Di Lorenzo, B.P. Finney, E.J. Gregr, C.E. Grosch, S.R. Hare, G.L. Hunt, J. Jahncke, N.B. Kachel, H. Kim, C. Ladd, N.J. Mantua, C. Marzban, W. Maslowski, R. Mendelssohn, D.J. Neilson, S.R. Okkonen, J.E. Overland, K.L. Reedy-Maschner, T.C. Royer, F.B. Schwing, J. X. L. Wang and A.J. Winship. 2007. Bottom-Up forcing and the decline of Steller sea lions in Alaska: Assessing the ocean climate hypothesis. Fish Oceanogr. 16:46-67

Yamanaka, K.L., Lochead, J.K., Cooke, K., Lacko, L.C. and Dykstra, C.  2007. Summary of non-halibut catch from the standardized stock assessment survey conducted by International Pacific Halibut Commission in British Columbia from May 31 to July 24, 2005. Canadian Technical Report of Fisheries and Aquatic Sciences 2689. 55 p.

## Section II:

## Research Proposed for 2008

Projects to be carried out in 2008 consist of a continuation of several projects currently underway. Six new projects are being proposed by the staff. Selected continuing projects include:

- Project 413.00 - PIT tag recovery efforts will continue in 2008 with the scan sampling program. Scanning will also continue on the assessment survey vessels.  No other changes are planned for port coverage or duration of sampling. Planning for this activity is based on a March 1 – November 15 season. At this time, 2008 is expected to be the final year of scanning.

- Project 621.00 - The study of the population genetic structure will continue in 2008 with the sample testing and analysis supervised by Dr. Lorenz Hauser (UW Marine Molecular Biology Laboratory). The FY2008 budget will allow for continued sample analysis by a technician in Dr. Hauser’s lab. We also are broadening the geographic scope by seeking samples from Atlantic halibut and also samples which have been offered by TINRO scientists in Vladivostok.

- Project 652.11 – A second year of examination of the hooking success by halibut on longline gear, using the Didson sonar. This effort follows up on the 2007 study and seeks to gather additional video observations, and will also look at the success rate on smaller circle hooks.

- Staff will also continue with other long-standing projects in 2007. These include the collaborative work on contaminants with ADEC (#642.00), placement of IPHC staff on the NMFS summer trawl surveys (#604.00), data collections with water column profilers on the assessment surveys (#610), and the undergraduate internship program (#618). The otolith marginal increment analysis (#626.00) is expected to be completed in 2008. Finally, the investigation of sleeper shark population structure and development of an aging technique (#630.00) will focus on lab work and genetic testing of samples.

Six new projects are proposed for 2008:

- Comparison of halibut catch rates on swivel gear and fixed hook gear - IPHC has been collecting information on the use of swivels in the halibut fishery since 2001. In 2001, 34% of the trips used swivel snap gear in B.C. (Regulatory Area 2B). This number rose to 46% in 2002, to 62% in 2003, and dropped slightly to 58% in 2004. This study will determine the effect of using swivels on the catch rates of species subject to longline gear.

- PAT tag deployments in Area 4 - The staff is proposing to release PAT tags in Area 4 in 2008 in an effort to determine the reasons why so few PIT tags were recovered in the Bering Sea halibut fisheries. Recoveries to date of PIT tags are far below what was expected. The releases would be made in batches of 20 tags in each of the Area 4 survey regions during the summer assessment surveys, for a total of 100. The large number of releases is expected to provide sufficient recoveries to enable estimation of fish movements.

- Pilot application of archival tags in Area 2B – This study will investigate migratory behavior and environmental conditions experienced by small adult (primarily male) and late pre-recruit halibut. These fish have not been studied with PAT tags due to the size constraints imposed by the large, bulky nature of the PAT tags, and to obtain multi-year data for larger fish. Externally attached, rather than surgically implanted, archival tags will be used in this project. The tags would be applied to all females above 90 cm and all fish above 100 cm, late in the season.

- Coastwide deployment of water column profilers on IPHC survey vessels –  The goal of this project is to implement a program to measure oceanic properties in the waters over the Alaskan, B.C., and the U.S. West Coast continental shelf that can be correlated to catch per unit effort (CPUE) of halibut as well as incidence of other groundfish species. Water column profilers that measure temperature, salinity, dissolved oxygen, pH, and florescence will be deployed at each station during the summer assessment survey. These data will provide an annual snapshot of nearshore oceanic conditions as well as valuable observational data for modeling and biological studies on recruitment and growth variability.

- Removal fishing to estimate catch probability – The proposal is to conduct removal sampling as a technique for directly estimating catch probability at a sample of setline survey stations in one regulatory area in 2008. These data will allow us to model catch probability as a function of station and individual fish covariates, and compute a population index for the area that accounts for catch probability.

- Bycatch characterization in the Pacific halibut fishery off Alaska:  A field test of electronic monitoring technology – While previous work on the use of EM to monitor longline operations off Alaska demonstrated the potential for this technology, the research was conducted under research conditions and not commercial fishing conditions. In the commercial fishery a much broader range of environmental and physical factors affect the vessel operations. As a result, these methods are not yet proven under commercial fishing conditions off Alaska. Partial funding for this project has already been secured through the North Pacific Research Board, and is being carried out in cooperation with the NMFS Groundfish Observer Program and the Pacific States Marine Fisheries Commission.

Projects conducted under contract to other agencies or through research grants will be continued in 2007. IPHC port sampling activities in Alaska will continue being augmented by a grant from NMFS (Project 375.00), and IPHC port samplers in Alaska will collect sablefish logbook data for the NMFS Auke Bay lab (Project 628.00). NPRB has provided a grant to offset some of the costs associated with the electronic monitoring pilot study (new #6).

We are also awaiting word from ODFW on a proposal to add stations to the Oregon survey region to look at rockfish indices.

Funded Research

#### Project 413.00: 	PIT tagging study:  Year 5 of tag recovery and scanning

Start Date:  2003

Anticipated ending:  2009

Personnel:	J. Forsberg, C. Blood, G. Williams, B. Clark, A. Ranta, scan samplers

Scanning for PIT tags will continue in 2008. IPHC will hire samplers for Alaskan ports, while contracting with AMR for the Canadian ports and continuing to seek state and tribal assistance in Area 2A. Sampler duties include scanning commercial deliveries for PIT tags, and conducting regular tests of detection and piece (fish) counts to measure accuracy of sample data. Project costs are expected to be about the same as last year. Modest increases are expected in salaries (cola) and our contract with AMR for sampling in Area 2B.

#### Project 604.00:	NMFS trawl survey:  At-sea data collection and IPHC data base management

Start Date:  1996

Anticipated ending:  Continuing

Personnel:  L. Sadorus, A. Ranta, B. Clark

A series of NMFS trawl survey data on halibut, parallel to our setline data, is extremely valuable to IPHC as a second fishery-independent data source for stock assessment. Trawl data are particularly useful because they include large numbers of juveniles (ages 3-7 yr) that do not appear in large numbers in the setline survey. Otoliths have been collected on the NMFS surveys since 1996 and provide relevant age information. These data are incorporated into a copy of the NMFS haul data, expanded to estimates of relative abundance and age/size composition by IPHC area (NMFS calculates estimates by INPFC area), and stored in a database at IPHC. Project cost is comprised of personnel and travel. In 2008, the staff is planning on placing one sampler aboard the NMFS survey vessel.

#### Project 610.11:	Water column profiler project (annual survey project)

Start date:  2000

Anticipated ending:  Continuing

Personnel:  L. Sadorus, S. Hare, P. Stabeno (NMFS PMEL)

The IPHC maintains one of the most extensive sampling platforms in the north Pacific. This platform offers enormous potential for collection of valuable oceanographic data. In particular, understanding the dynamics of the structure of the mixed layer depth – a major GLOBEC goal - requires in situ vertical profiling. Use of this platform for oceanographic data collection capabilities not only would benefit the scientific community at large, but demonstration of sampling feasibility may also create other funding opportunities for collaborative research. In 2001 and 2002, the IPHC successfully deployed a SeaBird SBE-19 water column profiler from a commercial fishing vessel participating in the annual stock assessment survey. The profiler has been used on selected survey trips each season since. Project cost is directed towards annual maintenance of the one profiler owned by IPHC.

#### Project 610.12:	Water column profiler project (Oregon grid)

Start date:  2007

Anticipated ending:  Continuing

Personnel:  L. Sadorus, S. Hare, P. Stabeno (NMFS PMEL)

Same equipment as in the previous project but used only on stations off the Oregon coast.

#### Project 618.00:	Undergraduate Internship

Start Date:  2002

Anticipated duration:  Continuing

Personnel:  L. Sadorus, T. Loher, other staff support as needed

One undergraduate will be selected through the intern/co-op programs at regional universities and colleges to do a combination of office and at-sea work based out of the Commission offices during the summer months. The program includes various pre-determined office tasks as well as being assigned a research project then designing and executing said project. A final report and presentation are given at the conclusion of the employment term.

#### Project 621.00:	Genetic population structure of Pacific halibut assessed via nuclear microsatellite diversity – lab work by UW

Start:  2002

Anticipated Ending:  Continuing

Personnel:  T. Loher, L. Hauser (UW-MMBL), other staff as needed

Results from a preliminary population analysis of the summer 2002 samples suggested potential reproductive isolation in the Aleutians. Tissue samples were collected in winter 2004 to address the question of whether or not the Bering Sea is reproductively isolated from the Gulf. The analyses of these by Dr. Lorenz Hauser (UW - Marine Molecular Biology Laboratory) are nearing completion. His lab is also continuing with the testing and analysis of the summer samples from 2005 and 2006, and would also begin analysis of the winter 2007 samples. Efforts would also be made to obtain samples from Russia, and the Canadian Atlantic for comparison.

#### Project 630.00:	Sleeper shark genetic studies

Start Date:  2003

Anticipated ending:  Continuing

Personnel:  S. Wischniowski, G. Williams

The objective is to determine if these sharks come from a homogenetic population. The population dynamics of sleeper sharks within the northeast Pacific is not well documented. Preliminary tagging studies have indicated that at least some sleeper sharks display a resident behaviour, and likely have relatively small home ranges. To test this assumption tissue samples were collected from live sharks by way of biopsy darting during the 2004 summer assessment survey. A simple test of homogeneity will compare samples collected from regions of high occurrence to peripheral regions of lesser occurrence. All tissue samples for this project have been collected, and no additional samples are needed. This portion of the research proposal will specifically target the analysis aspect of the study.

Mitochondrial DNA polymorphisms will be used as the initial genetic marker system to investigate population differentiation among the three sampling locations. We will initially attempt amplification using primers located within the proline tRNA and 12S rRNA regions of the mitochondria. These primers have been used to examine population genetic structure across a similar geographic range in blacktip sharks and yielded sufficient information to differentiate among nurseries of this species. Statistical analysis will be by way of X2 and AMOVA probabilities of haplotype homogeneity across sampling sites. Extraction of mitochondrial DNA from skin samples, polymerase chain reaction (PCR) amplification and sequencing will occur in the Microbiology Lab at the Department of Microbiology, University of Victoria, B.C.

#### Project 636.00:	Analysis of gonad staging on IPHC setline surveys (histology)

Start:  2004

Anticipated Ending:  Continuing

Personnel:  T. Geernaert, C. Dykstra, other staff as needed

The IPHC Stock Assessment surveys assess maturity of halibut based on visual criteria established in the early 1990’s and modified in 1995. These survey data combined with the age data are important components in the stock assessment model. Four maturity stages are presently assigned to female halibut; immature (F1), maturing (F2), spawning (F3) and resting (F4). Once a female halibut has spawned, the gonad transitions to a resting phase, back to maturing, and then to spawning again. Our criteria for classification also assume that the immature (F1) stage is only seen with immature fish but we are seeing anomalies during the survey that could question this assumption. Mature females are seen as small as legal size (82 cm) but, area-wide, there have been several large 100+ cm females whose gonadal characteristics classify them as immature (never spawned). The SSA survey data also suggest that fish in the southern latitudes (Area 2B) mature earlier and possibly spawn earlier that fish in the northern latitudes (Area 3A and west). The timing and duration of these events are not clearly understood. We would like to re-evaluate our classification criteria and examine the stages and gonadal tissue development more closely.

In 2003 preliminary histological work on the female gonads was initiated. We developed a sampling design and collection protocols for the 2004 surveys. In 2004, during winter and summer surveys, female gonads from three different regions, in each stage of development, were collected. Three different histological subsamples have been prepared and we are presently standardizing the sample sites on the gonad for the final slide preparation. We have collected nearly 240 gonad pairs and will be analyzing multiple sites from each sample in 2007.

#### Project 642.00:	Assessment of mercury and contaminants in Pacific halibut

Start Date:  2002

Anticipated ending:  Continuing

Personnel:  C. Dykstra, Alaska Department of Environmental Conservation (ADEC)

For the last few years, health officials and media have raised the profile of pollutant contamination in fish (methyl mercury, PCB’s, pesticides). Since 2002, the IPHC has been working collaboratively with the Alaska Department of Environmental Conservation (ADEC) to collect halibut tissue samples to be analyzed for heavy metal and organic pollutant loading. The principal results from the 2002 collection led the Alaska Division of Public Health in 2003 to conclude that the concentrations of heavy metals in Alaskan Pacific halibut are not a public health concern. In 2004 the first results regarding organic pollutants (PCB’s, pesticides) were released demonstrating that halibut had the lowest concentrations of the five species (including salmon and sablefish) examined. Since 2002 the IPHC has submitted 618 samples for testing by ADEC. The mean level of total mercury for these samples has been 0.348 ppm (for comparison the FDA limit of concern for methyl mercury is 1.000 ppm, the EPA and the CFIA level of concern is 0.500 ppm) ranging from non-detectable to 1.947 ppm. The IPHC and ADEC are continuing to qualify the data with physical parameters (age, size, and weight) and additional analyses will be done on the samples. ADEC and EPA planned on going ahead with this study regardless of IPHC input. Our involvement in the project has allowed us to provide input on study design, sampling protocols in the field, etc., which will make the resultant information much more robust.

Sampling continued in 2007 with a targeted collection of 60 samples (20 fish between 10-20 lbs, 20 fish between 20-40 lbs and 20 fish greater than 40 lbs.) from each of three regions (Fairweather, Trinity, and Attu) during the setline survey. An additional 97 samples where collected from two Attu stations that produced what appears to be anomalously high readings in 2005. Results will be published as they become available. ADEC has expressed interest in further assessments of contaminant occurrence in halibut in 2008.

#### Project 650.00:	Archival tagging – pilot studies

Start Date:  2006

Anticipated ending:  Continuing

Personnel:  T. Loher

PAT tags represent a powerful tool for studying the movement and behavior of adult halibut, but their relatively large size has so far prevented us from extrapolating the results across population components. PAT tags have only been deployed on fish larger than 105 cm fork length (FL) and most halibut of this size are female. It is reasonable to examine whether males and non-reproductive individuals behave differently than large females. Sex-specific migratory behavior is common in many species because males and females typically do not possess the same annual energy budgets and potential for long-distance dispersal. This study represents a controlled test of the relative utility of three different models of internal archival tag that can be used on relatively small (60-99 cm FL) halibut. In August 2006, halibut ranging from 65-90 cm FL were transported to the Oregon Coast Aquarium in Newport, and fifteen were surgically implanted with archival tags in October. Five fish were tagged with each of 3 different tag varieties: 1) Lotek LTD 1110, an 11 mm by 32mm resin-body tag, 2) Lotek LTD 2310, a 16 mm by 76 mm silicon-coated stainless steel tag with a 24 cm external light stalk, 3) Wildlife Computer MK9, a 17 mm by 67 mm resin-body tag with a 19 cm external light stalk. All tag varieties record temperature and depth, and the tags with light stalks are capable of recording ambient light for the purpose of estimating fish location. All fish survived the implantation process, although one died in July due to a large temperature fluctuation at the holding facility. The one-year holding period has just concluded and fish will be sacrificed during the first week of December. They will be examined internally to assess any potential reactions to the internal tag, and we will also use this opportunity to determine the feasibility of non-invasive sex determination via veterinary ultrasound, so that future tagging can be conducted in a sex-specific manner.

#### Project 652.11:	Verification of hooking success using Didson sonar

Start Date:  2007

Anticipated ending:  Continuing

Personnel:  S. Kaimmer, S. Wischniowski

The purpose of the study is to verify, by direct observation, the halibut hooking success curve for halibut on setlines. This curve has been estimated from tag release/recovery data and from a small set of direct observation data collected with an underwater video camera in shallow waters. This project would generate a larger set of observations and operate in more appropriate depths. During 2005 and 2007, the IPHC conducted gear studies aimed at estimating the effects of hook size and hook spacing on setline catches. The 2007 Hooking success (#652.00) study developed a gear selectivity curve for large circle hooks based on direct observation of hook attacks and hooking success. This continuation will expand the current study to include observations on smaller hook sizes. The conclusions of this continuation study will be valuable in interpreting the results of the 2007 hook size and spacing study, giving direct observations on hook attacks and more importantly hooking success as a function of halibut length.

#### Project 653.00:	Species identification of amphipods frequenting Pacific halibut

Start Date:  2006

Anticipated ending:  Continuing

Personnel:  B. Leaman, E. Soderlund

The project intends to document the occurrence and virulence of attacks by predatory amphipods on halibut caught on IPHC surveys and, by inference, the commercial fishery. The commercial industry suffers annual losses of product due to amphipod predation and must adjust its fishing locations and practices in response to predation. Harvester discussions indicate that predation sites are both known and ephemeral, and the virulence may vary interannually at a given site. The specific identity of the amphipods has not been established and it is probable that more than one species is involved. Harvesters are interested in both documentation of predation areas for avoidance, as well as gaining an understanding of the dynamics of the species at given sites, i.e., are there cycles of abundance that respond to other factors. Data were collected on all stations during the 2004, 2005, and 2006 stock assessment surveys as part of standard protocol, recording incidence of sand flea predation, and the extent and virulence of the predation. The 2006 was the last year of data collection for this stage of the project. The 2007 summer intern performed initial analysis of interannual occurrence and virulence. Additional work will be directed at correlated variables.

Proposed New Research in 2008

#### Comparison of halibut catch rates in swivel gear

Start Date:  2008

Anticipated ending:  2008

Personnel:  S. Kaimmer, K. Gravel, Survey team

IPHC has been collecting information on the incidence and use of swivels in the halibut fishery since 2001. In 2001, 34% of the trips used swivel snap gear in Area 2B. This number rose to 46% in 2002, to 62% in 2003, and dropped slightly to 58% in 2004. This study will determine the effect of using swivels on the catch rates of species subject to longline gear.

We are still in the design stage at this point. Some issues being examined include the area in which the study will operate, the number of comparison sets and subsequent fishing trips, specific gear configurations to test, and potential amount of rockfish bycatch.

#### PAT tags:  summer releases in Area 4

Start Date:  2008

Anticipated ending:  2009

Personnel:  T. Loher, B. Clark, sea samplers

The staff is proposing to release PAT tags in Area 4 in 2008 in an effort to determine the reasons why so few PIT tags were recovered in the Bering Sea halibut fisheries. Recoveries to date of PIT tags are far below what was expected. The releases would be made in batches of 20 tags in each of the Area 4 survey regions during the summer assessment surveys, for a total of 100. The large number of releases is expected to provide sufficient recoveries to enable estimation of fish movements.

#### Archival tags:  pilot releases in Area 2B

Start Date:  2008

Anticipated ending:  2009

Personnel:  T. Loher

This study will investigate migratory behavior and environmental conditions experienced by two components of stock:  small adult (primarily male) and late pre-recruit halibut, as well as larger adults including reproductive females. The work is a complement to PAT (satellite) tagging studies and seeks to expand our knowledge to components of the population that have not been studied with PAT tags due to apparent size constraints (i.e., males and pre-recruits) and to obtain multi-year data for larger fish. The objectives for each stock component are slightly different, but do not require separate studies. Externally attached, rather than surgically implanted, archival tags will be used in this project. The tags would be applied to all females above 90 cm and all fish above 100 cm, late in the season. Attachment protocols will be determined over the spring and summer of 2008.

The depth data from the tags will be used to quantify: 1) mean timing and duration of fall departure to deep water, 2) mean deep-water residence period, 3) mean active spawning date, 4) mean active spawning depth, 4) mean timing and duration and the spring return to shallow water, 6) proportion of the tagged population failing to make a fall migration, 7) proportion of the tagged population failing to display spawning rises, 8) differences between male and female fish, and eventually 9) regional variance in all the above parameters (presuming sample sizes allow meaningful comparisons). Along with means, of particular interest will be fitting descriptive functions to the range of data (such as described earlier for the rise initiation date data).

#### Coastwide water column profilers for IPHC survey vessels

Start Date:  2008

Anticipated ending:  Continuing

Personnel:  L. Sadorus, S. Hare, P. Stabeno (NMFS PMEL)

The goal of this project is to implement a program to measure oceanic properties in the waters over the Alaskan, B.C., and the U.S. West Coast continental shelf that can be correlated to catch per unit effort (CPUE) of halibut as well as incidence of other groundfish species. The IPHC operates a survey that covers the area, and water column profilers that measure temperature, salinity, dissolved oxygen, pH, and florescence will be deployed at each station. These data will provide an annual snapshot of near shore oceanic conditions as well as valuable observational data for modeling and biological studies on recruitment and growth variability.

To better understand the factors driving fluctuations in growth and recruitment of fish populations, increasing attention is being paid to climatic and oceanic conditions. Primary and secondary productivity are directly driven by variations in water temperature, salinity, oxygen, mixing, and light penetration, among other factors. Most of this production takes place in the mixed layer, between 20 and 100 meters depth. Spring and early summer are peak periods of production. Waters over the continental shelf are, naturally, most important to the groundfish species that constitute much of the fish production of the northeast Pacific. Observations of ocean conditions are important both to understand variability in time and space as well as to provide necessary data for modeling productivity. Satellites sample the ocean surface and free drifting arrays of mid-ocean profilers (Davis 1991, Feder 2000) provide data on mid-latitude ocean conditions. Moorings provide continuous hydrographic and current data but at fixed points. More recently, gliders have been employed to survey cross-shelf transects, but these units are very expensive. Generally, there is a great lack of observational data for most of the near shore northeast Pacific.

Capital expenditures for this project consist of the acquisition of 14 profilers from Sea-Bird Electronics (Bellevue, WA) and 14 laptop computers to accompany each profiler at sea. The amount budgeted for these expenditures is based on a quote provided by Sea-Bird in February 2007 and is good for one year. The quote includes a quantity discount and an additional discount due to IPHC’s non-profit status.

#### Removal fishing – pilot study

Start Date:  2008

Anticipated ending:  2009

Personnel:  R. Webster

Our proposal is to trial removal sampling as a technique for directly estimating catch probability at a sample of setline survey stations in one regulatory area in 2008. For the selected stations, a sequence of five sets will be made on consecutive days. The first set will be the standard survey set. Subsequent sets will use the same methods and collect the same data on halibut and station conditions as standard survey sets. These data will allow us to model catch probability as a function of station and individual fish covariates, and compute a population index for the area that accounts for catch probability. Some design and analysis issues remain to be worked out, in particular, whether migration of fish during the sampling at each station can be accounted for in the modeling.

#### Alaska fishery electronic monitoring – pilot study

Start Date:  2008

Anticipated ending:  2009

Personnel:  G. Williams, B. Leaman, B. Karp and J. Cahalan (NMFS Observer Program)

Bycatch rates in the Pacific halibut fishery are not well estimated. The majority of vessels operating in this fishery are not required to have NMFS/NPGOP monitoring; hence estimates of bycatch are not based on direct observation of the fishery. The long term focus of this research is to improve our understanding of the ecosystem impacts of halibut fishing through improved monitoring of longline fishery bycatch and to provide data on mortality of bycatch species for input to stock assessments. We will be comparing and evaluating the effectiveness of electronic monitoring (EM) and the currently utilized National Marine Fisheries Service (NMFS), North Pacific Groundfish Observer Program (NPGOP) monitoring methods to operate effectively in a commercial longline (hook-and-line) setting in Alaskan waters. This is a cooperative study with the commercial fishing industry and relies on our ability to sample on various vessel configurations.

Previous research by one of the partners in this proposal documented successful EM of Pacific halibut longline fishing from chartered research vessels (Ames, 2005; Ames et al., 2007). While this work supported the use of EM to monitor bycatch, the research was not conducted under commercial fishing conditions. In the commercial fishery a much broader range of environmental and physical factors affect the vessel operations. As a result, these methods are not yet proven under commercial fishing conditions off Alaska. Partial funding for this project has already been secured through the North Pacific Research Board.

#### False annuli identification in juvenile halibut ages one to four

Start Date:  2008

Anticipated ending:  2009

Personnel:  S. Wischniowski

The purpose of the study is to address the question of otolith annuli and check interpretation. Is the age and growth lab correctly assigning ages based on its definition of a translucent growth zone compared to a check? The Bering Sea has demonstrated to produce growth patterns in which this interpretation may be in question. To address this issue selected samples of both “typical” and “atypical” growth zones will be analyzed both chemically and morphometrically. First, LA-ICP-MS will be utilized to determine if the elemental constituency of an otolith changes between growth zones. LA-ICP-MS will be utilized to raster selected areas of summer growth, winter growth, and suspected checks of thin-sectioned otoliths to determine if chemical signatures differ between these rastered areas. Specifically, we wish to determine if a check has a different chemical signature when compared to its neighboring translucent zone(s). Second, MIA will be used to quantify the percent occurrence of juvenile halibut that demonstrate similar occurring check patterns. All translucent and check zones will be measured from the focus to quantitatively characterize each otolith’s microstructure. Results will then be compared among geographic regions to test for statistically significant check (microstructural) patterns that may be associated to location of capture.

Other 2008 Research – Contracts and Grants

#### Project 375.00:	Alaska port sampling

Start Date:  2002

Anticipated ending:  Continuing

Granting agency:  NMFS

Personnel:  H. Gilroy, M. Larsen, L. Hutton

The commercial fishery port sampling program hires samplers to collect otoliths, halibut lengths, fishing logbook information and landed weight data. The U.S. program includes staffing eight Alaskan ports and Bellingham, Washington. The samplers act as the liaison between the fishing industry and the Commission staff in Seattle. The Commission is responsible for the overall assessment and management of the halibut fishery and the data collected are necessary for stock assessment. The U.S. Government adopted the Individual Fishing Quota (IFQ) allocation program in 1995. This grant provides funds to the IPHC for the incremental cost to the Commission sampling program due to the IFQ program. The grant is generated from the NMFS IFQ Fee Collection Program.

#### Project 628.00:	Alaska catcher vessel logbook and sablefish data collection

Start Date:  1999

Anticipated ending:  Continuing

Granting agency:  NMFS

Personnel:  L. Hutton, H. Gilroy, A. Taheri, port samplers

IPHC and NMFS Auke Bay Lab (ABL) have a sablefish data collection program. The program was reviewed and modified in 2003/2004 to meet the IPHC confidentiality policy and to encompass all vessels rather than just vessels greater than 60 feet. Under a Statement of Work, NMFS contracted IPHC staff to interview the IFQ fishers to review and collect the sablefish information in addition to the halibut information. Data are entered by IPHC staff with an electronic summary provided to the NMFS ABL scientists. In the summarized data, the vessels are assigned a unique code to preserve confidentiality.

IPHC and NMFS Auke Bay Lab (ABL) have a sablefish data collection program. The program was reviewed and modified in 2003/2004 to meet the IPHC confidentiality policy and to encompass all vessels rather than just vessels greater than 60 feet. Under a Statement of Work, NMFS contracted IPHC staff to interview the IFQ fishers to review and collect the sablefish information in addition to the halibut information. Data are entered by IPHC staff with an electronic summary provided to the NMFS ABL scientists. In the summarized data, the vessels are assigned a unique code to preserve confidentiality.

Research Conducted Without Direct Funding

#### The 2007 stock assessment

Personnel:  B. Clark, S. Hare

The annual stock assessment process comprises a large amount of work including preparation of IPHC data, estimation of bycatch by length in other fisheries, model development and validation, model fitting, examination of residuals, comparison of alternative model specifications, sensitivity tests, evaluation of harvest strategy, incidental analyses, and reporting.

#### Development of IPHC harvest policy

Personnel:  S. Hare, B. Clark

Staff quota recommendations are calculated by applying a judiciously chosen harvest rate to an estimate of present exploitable biomass. The constant harvest rate policy was developed on the basis of its performance over a long time horizon and with the explicit goal of avoiding reaching the minimum stock sizes seen in the 1930s and 1970s. In 2003 the staff proposed a conditional constant catch policy under which total removals would be capped at a chosen ceiling level at high biomass levels, while a constant harvest rate policy would continue to be employed at low and intermediate stock levels. The Commission did not adopt the proposed policy at the 2004 annual meeting, and a staff/industry workshop on harvest policy alternatives in September 2004 showed general satisfaction with the present policy, as mediated in practice by the judgment exercised by the Director in developing staff recommendations and by the Commission in finally setting catch limits. In 2004, an explicit lower limit on spawning biomass and a threshold below which the harvest rate will be reduced—were added to the constant harvest rate policy. As a result the target constant harvest rate for the core IPHC areas (2B, 2C, and 3A) was lowered to 22.5% from 25%. The staff will continue to evaluate the constant harvest rate policy. In particular, we will recalculate the optimum harvest rate itself in light of our present understanding of stock dynamics and new information on commercial length-specific selectivity coming from the PIT tag experiment.

#### Development of a robust management procedure

Personnel:  B. Clark, S. Hare, B. Leaman

Staff catch limit recommendations are derived from the annual stock assessment by applying a constant harvest rate to the estimates of exploitable biomass, in the belief that the assessment model is correctly specified and the estimates are accurate. In fact there are a number of structural uncertainties about the model, and the assessment itself has become highly complicated, so it is vulnerable to any small error in data compilation or programming. The aim of this project is to develop a procedure for deriving catch limit recommendations that would achieve the desired harvest policy, potentially relying on much simpler calculations and at the same time be effective across a range of uncertainties about stock, fishery and management behavior. Such procedures have been developed for other fisheries and it is appropriate to investigate their application to halibut management.

#### Estimation of halibut abundance from mark-recapture data

Personnel:  R. Webster, B. Clark, B. Leaman

The IPHC has conducted many tagging programs since the 1920s. IPHC has also conducted at least five reviews of these programs, again with differing objectives. However, many of these reviews did not account for the issues of non-reporting or differential reporting of tags by areas, fishing effort effects on recovery probabilities, the relationship of initial tag releases and the density of fish in given areas, and the effect of seasonal migratory patterns on the analysis of recoveries were not always considered. A changed paradigm for the area-specific impacts of juvenile bycatch, questions concerning the effects of changing seasonal distribution of fishing effort, potential halibut distribution changes with climatic shifts, and the utility of juvenile surveys in specific areas have all prompted concerns about halibut movements.

The staff marked the catch of three skates at each survey station coastwide in 2003 and in Areas 2B and 3A in 2004. Preliminary analysis of the 2004 recoveries showed good agreement with the stock assessment in Areas 2B and 2C, but farther west the mark-recapture estimates were much higher than the assessment estimates. Recoveries in 2005-2006 followed a similar pattern. The 2007 recoveries will be added to the analysis this year.

#### Seabird occurrence project

Start Date: 2002

Anticipated ending: Continuing

Personnel:  T. Geernaert, Washington State Sea Grant

During the 2004 stock assessment surveys, sea samplers counted the number of seabirds in the vicinity of the vessels following gear retrieval. This is the third year the seabird occurrence data were collected on IPHC surveys. Sampling after the haul addresses the question of where and when certain seabird species occur. Ultimately, these data might be used to identify appropriate seabird deterrent requirements in certain geographic locations, especially for the halibut fleet. IPHC has developed a database to store seabird occurrence data from the IPHC stock assessment surveys, as well as the NMFS and ADF&G sablefish surveys. The data are currently being analyzed. IPHC, in coordination with Washington Sea Grant, will be writing a joint paper on the results for the 2002-2004 data. The collection project is ongoing.

#### Seabird data repository (Project 643)

Start Date:  2005

Anticipated ending:  Continuing

Personnel:  T. Geernaert

This project encompasses the storage by IPHC of various types of seabird data collected on agency surveys, including the seabird occurrence project conducted on the assessment surveys. Although IPHC has been collecting these data on its assessment survey since 2002, other agencies are just beginning the same procedure. IPHC’s head-start with these types of data led other programs to seek the efficiencies provided by IPHC in data management for optimal use by analysts and managers. A grant from Washington Sea Grant funded this activity in previous years.

#### Estimates of bycatch on the setline surveys

Start Date:  2003

Anticipated ending:  Continuing

Personnel:  C. Dykstra, Survey Team, and DFO personnel

Area 2A

Since 2002, the IPHC has worked cooperatively with both the Washington Department of Fish and Wildlife (WDFW) and Oregon Department of Fish and Wildlife (ODFW) to collect rockfish bycatch data. All rockfish caught on operations in 2A are marked with an external Floy tag and the tag number is recorded with the set (and recently the skate number) information. All marked fish were retained for sale. At the offload, a state biologist meets the vessel and samples the rockfish for length, weight and maturity, takes a genetic sample and otolith. The IPHC then provides each agency with the effort information collected as part of the normal survey data collection.

In 2007, IPHC and Washington Department of Fisheries received funding from Pacific States Marine Fish Commission (PSMFC) for the second year of a join project with industry. The Washington survey region was expanded to include 18 special stations (ten of which where fished in 2006, and eight were new locations for 2007) to look at rockfish populations. Stations were selected by WDFW with the hope of targeting rockier bottom than traditionally fished by the standard survey stations in the Washington region, so as to better characterize rockfish abundance. Three skates of gear where fished at each station as a precautionary approach due to the exploratory nature of these stations and concerns for over fishing yelloweye rockfish. Activities at each station were identical to those on standard IPHC stations, and rockfish were handled as described above. A summary of this project will be submitted to PSMFC by the end of November 2007. Depending on those results, there may be a third season of sampling under this funding opportunity.

Area 2B

In 2007, IPHC worked with DFO to provide a third biologist on IPHC survey vessels to sample rockfish. While this is the fifth year of the extensive bycatch sampling program in Canada, it is the first year that the IPHC trained and deployed the third biologist (previous years the third was provided by Archipelago Marine Research Ltd.). The program was funded by industry (Pacific Halibut Management Authority). Data collected included hook by hook occupancy information for all species, and otoliths, maturities, and lengths for rockfish. Continued collaboration is anticipated.

Area 2C and eastern 3A

In 2007, IPHC worked cooperatively with Alaska Department of Fish and Game (ADFG) to collect rockfish bycatch data. Rockfish caught in the Ketchikan, Ommaney, Sitka, Fairweather and Yakutat charter regions were marked with an external Floy tag and the tag number was recorded with the set and skate capture information. All marked fish were retained for sale. At the offload, state biologists (contract biologist for BC landings) would meet the vessel and sample the rockfish for length, weight, maturity, and the otolith. The IPHC then provides each agency with effort information collected as part of the normal survey data collection. This was a developmental year for this sampling effort and it evolved somewhat over the course of the season. As not all offloads were met by biologists, the IPHC samplers assisted with the data collection where possible. Additionally the work focused on demersal shelf rockfish (DSR), with the subsampling being constrained to those species. The IPHC did collect piece count observations for all rockfish involved despite the focus on DSR specimens.

Area 4

The IPHC collected retention/non-retention information on Pacific cod for landings coming into Dutch Harbor and St. Paul. Survey vessels recorded the number and pounds of Pacific cod retained and discarded by survey station. This information was collected when the vessel initiated retention of Pacific cod which usually started four days from the expected landing date. Additional subsamples from the retained Pacific cod were obtained opportunistically from the survey offloads by IPHC port sampling staff. This included piece count information and length data. This was part of a developing effort to collect bycatch information on Pacific cod in the western regions of our survey, where it makes up the largest component of our survey bycatch.

#### Sleeper shark investigations:  Ageing study (Project 630)

Start Date:  2003

Anticipated ending:  Continuing

Personnel:  S. Wischniowski, G. Williams

The Pacific sleeper shark (Somniosus pacificus) age determination program commenced in 2005. Selected samples were cleaned of extraneous meat and connective tissues and sliced into 5mm thin-sections. It soon became evident that difficulties in the pre-staining preparation phase were going to be encountered. Pacific sleeper sharks lack a great deal of calcification to their vertebra, this structure can best be described as a “cartilagic garden hose”. The entire vertebra is almost completely composed of cartilage, and lacks any hardened surfaces including the centra (structure typically utilized to age sharks). These centra can best be described as thin membranes similar to the tympanic membrane of the inner ear in mammals. As fragile as this structure is, it more than likely does not function as the site of articulation as in most vertebrates. It is surmised that these centra might function as a means of regulating and controlling spinal fluid pressure within the vertebra. Specimen “A” (our first test sample) was recorded to have ~ 75 ml of spinal fluid in-between its two centra. It is possible the animal might gain structural support by retaining a turgid environment within its vertebra.

Further difficulties were encountered when the centra was removed and dried. Water loss resulted in a large amount of shrinkage and cracking which prevented further manipulation of this structure. Current experiments are ongoing to determine which methodology works best to retain hydration of the structure prior to staining. Both EtOH and glycerin (without thymol) are currently being investigated.

#### Review of port sampling, 1994 to present

Start Date:  2002 (Deferred in 2004)

Anticipated ending:  2008

Personnel:  L. Hutton, T. Kong

Report on the changes that have occurred in the commercial catch sampling and port sampling program from 1994 to the present. For example, the report will review the changes made to the program due to the implementation of the IFQ fishery in Alaska, the changes in the method of logbook data collection in the U.S., as well as changes in the Canadian program. This is an update of Technical Report 32.

#### Electronic reporting project for commercial landings in Alaska

Start Date:  2002

Anticipated ending:  Continuing

Personnel:  H. Gilroy, L. Hutton, T. Kong, A. Tesfatsion, H. Tran

IPHC, ADF&G, and NMFS staffs have worked with contractors initially hired by Pacific States Marine Fisheries Commission (PSMFC) to implement a cooperative interagency electronic fishery reporting system for commercial landing records in Alaska. The project included designing a web based Interagency Electronic Reporting System (IERS) with the repository database in the State Office Building in Juneau. In May 2006, IERS was optional for statewide groundfish landings and IFQ/CDQ halibut and sablefish. Since the program is operational 24/7 the agencies are working with an outside company to provide help desk support during non-business hours. For halibut, the system reduces duplicative reporting resulting from the current requirements of completing ADF&G fish tickets and NMFS RAM quota share reports. The application (eLandings) records data elements required by regulations, prints fish tickets, and connects with the NMFS quota share database. The appropriate data from IERS is being sent to the agencies for their internal databases. The application allows processors to import or export data into their own databases so double entry is not necessary. The project is ongoing and industry personnel and agency staff have provided feedback on the operation so the application will continuously be modified to add additional features. In 2007, additional fisheries will be added including statewide shellfish.