## Slide 1: Fishery Disaster and CARES Act Update
August 23, 2022
David Briggs
Pacific States Marine Fisheries Commission

## Slide 2: OUTLINE
Overview
Disasters
CARES Act/COVID Relief

## Slide 3: PSMFC’s Role
Provide Administrative oversight
Coordination of activities with varies entities/parties
Ensure Compliance with Award Terms and Conditions
  Programmatic/Legislative
  Financial
  Reporting
Maintain adequate records and necessary documentation for audit

## Slide 4: TIMELINES
Fishery Disaster approved by Secretary of Commerce
Funds approved by Congress
Commission receives notification from NOAA of funding
Commission prepares a Grant Application for funding
OMB appropriates funds to NOAA/NMFS. NMFS submits grant application to NOAA Grants Office
Meetings and Conference calls with Agencies/States to discuss process and requirements (Affidavits, Spend Plan, Applications)
Commission receives Grant Award from NOAA Grants Office
Detailed spend plans submitted to PSMFC to begin designing applications
  For CARES: PSMFC submit drafts to NMFS staff for review, comments, requests for revised spend plans
  Spend plans finalized by agencies. PSMFC submits final spend plan to NOAA Grants Office for approval.

## Slide 5: TIMELINES (cont.)
  PSMFC receives approval from NOAA Grants Office on spend plan.
  PSMFC staff works with agency staff designing application specific to spend plan criterial/eligibility/requirements.
Applications finalized
Postcards mailed to all potential eligible applicants
Application period begins
PSMFC website updated
Completed applications sent to PSMFC

## Slide 6: FISHERY DISASTERS COMPLETE
2006 Klamath River Commercial Salmon - $60 million
2008 Sacramento River Commercial & Recreational Salmon - $170 million
2007 Fraser River Sockeye WA Non-Tribal- $646,000
Yukon River Commercial Salmon - $5 million
2010, 2011, 2012 Yukon River, Kuskokwim, Cook Inlet AK Chinook Salmon - $20,776,727

## Slide 7: FISHERY DISASTERS ACTIVE
2016 Gulf of AK Pink Salmon - $56,284,970 (expires June 30, 2023)
2015 WA Coastal Salmon (Non-Tribal), 2016 Ocean Salmon Troll and charter (Non-Tribal), 2015-2016 CA Crab - $27,311,101 (expires April 30, 2023)
2014 Fraser River Sockeye Salmon, 2015 WA Coastal Salmon, 2015 South Puget Sound Salmon, 2016 Klamath River Chinook, 2015 WA Crab- $35,581,187, expires April 30, 2023
2013 Fraser River Sockeye Tribal and Non-Tribal, 2015 Coastal Coho and Pink Tribal Salmon, 2015-2016 CA Pacific Sardines, 2016 Ocean Troll Tribal Coho and Chinook, 2016-2017 Klamath River Fall Chinook Tribal and Non-Tribal- $18,919,062, expires April 30, 2024
2018 AK Chignik Sockeye Salmon - $10,316,712, expires July 31, 2025
2018 Gulf of AK Pacific Cod - $24,392,023, expires July 31, 2025
2016 & 2017 CA Red Sea Urchin, 2017-2019 CA Pacific Sardine, 2018 Yurok Tribe Klamath River Fall Chinook - $7,766,541, expires July 31, 2024

## Slide 8: FISHERY DISASTERS DECLARED/PENDING NOTIFICATION
2018 Upper Cook Inlet East Side Set Net and 2020 Upper Cook Inlet Salmon Fisheries
2018 Copper River Chinook and Sockeye Salmon Fisheries, 2020 Prince William Sound Salmon Fisheries, and 2020 Copper River Chinook
2019 Alaska Norton Sound Red King Crab
2019/2020 Eastern Bearing Sea Tanner Crab
2020 Gulf of Alaska Pacific Cod
2020 Alaska Norton Sound, Yukon River, Chignik, Kuskokwim River, and Southeast Alaska Salmon Fisheries
2021 Yukon River Salmon Fishery

## Slide 9: CARES (Round 1) DISBURSEMENTS TO DATE
TO MEMBER STATES
$131,391,111
OREGON
$15,804,589
WASHINGTON
$38,286,248
CALIFORNIA
$17,932,143
ALASKA
$49,508,407
CARES
$144,575,921
TO HI & Territories
$8,791,427
PSMFC
$521,288
(0.3%)
TRIBES
$3,872,095
WA Tribes Addendum
$8,928,197
AK Tribes
$931,527

## Slide 10: CARES Act Round 1 – Remaining
PSMFC Admin - $55,714
TRIBES - $1,103,058
CALIFORNIA - $212,982
OREGON - $28
ALASKA - $0
WASHINGTON - $2,222,549 ($277,092 state + $1,945,457 tribes)
HAWAII & TERRITORIES - $3

## Slide 11: CARES ACT Round 1 - Processing
CARES Act for States and Territories (Round 1) - $143,215,419
  PSMFC Admin Cost - .043%
  Spend plans submitted for approval: 31
  Funds distributed to date: $140,182,537
CARES Act for West Coast Tribes - $5,061,849
  PSMFC Admin Cost - .017%
  Spend plans submitted for approval: 30
  Funds distributed to date: $3,872,095

## Slide 12: CARES ACT Round 1 - Processing
Hawaii – spend plan approved 10/30/2020:
  364 applications received
  284 applications processed for payment
  80 applications disqualified or ineligible
California - spend plan approved 7/29/2020:
  11,527 applications mailed
  2,271 applications processed for payment
  545 applications disqualified or ineligible
Oregon – spend plan approved 7/29/2020:
  410 applications received
  304 applications processed for payment
  106 applications disqualified or ineligible
Alaska – spend plan approved 2/25/2021:
  6,710 applications received
  6,203 processed for payment
  507 applications disqualified or ineligible
Washington – spend plan approved 2/5/2021:
  810 applications received
  682 applications processed for payment
  128 applications disqualified, ineligible, or late
WA Addendum – 23 Tribes through subawards
Guam – spend plan approved 10/20/2020:
  785 applications received
  554 applications processed for payment
  231 applications disqualified, ineligible, or late
CNMI – spend plan approved 11/9/2020:
  1,176 applications received
  1,173 applications processed for payment
  3 applications disqualified, ineligible, or late
American Samoa – spend plan approved 11/3/2020:
  374 applications received
  248 applications processed for payment
  126 applications disqualified, ineligible, or late

## Slide 13: CAA (CARES 2) PLAN
TO MEMBER STATES
$107,282,604
OREGON
$13,278,484
WASHINGTON
$39,379,255
CALIFORNIA
$15,245,610
ALASKA
$39,379,255
CARES 2
$115,676,416
TO HI & Territories
$7,745,333
PSMFC
$648,479
(0.6%)

## Slide 14: CAA/CARES 2 – Remaining
PSMFC Admin - $466,837
CALIFORNIA - $15,245,610
OREGON - $13,278,484
ALASKA - $39,379,255
WASHINGTON - $39,379,255
HAWAII & TERRITORIES - $6,961,605
  Guam is complete ($783,728)

## Slide 15: CAA/CARES 2 – Execution
Wrapping up review of California applications now with existing staff; approximately 70% complete
Augmenting staff with contract staff to support application processing
Funds expire July 2023
  Targeted completion May 2023
Heavy use of lessons learned; striving to optimize application handling
Project lead to take on more quality-control tasks

## Slide 16: CARES Act Round 2 – Front End Processing
Hawaii:
  Final spend approved by NOAA Grants – 7/23/2021
  Postcards mailed to participants – 8/16/2021
  Application available on website – 8/16/2021
  Application deadline - 9/30/2021, 45-day after posting on website
California:
  Final spend approved by NOAA Grants – 9/28/2021
  Postcards to be mailed to participants – 9/22/2021
  Application available on website – 10/4/2021
  Application deadline - 11/17/2021, 45-days from posting on website
Alaska
  Final spend plan approved by NOAA Grants – 10/26/2021
  Postcards mailed to participants – week of August 1st, 2022
  Application available on website – 7/29/2022
  Application deadline – 10/31/2022, 95-days after posting on website
Washington
  Final spend approved by NOAA Grants – 11/1/2021
  Postcards mailed to participants – 6/30/2022
  Application available on website – 7/1/2022
  Application deadline - 10/15/2022, 45-day after posting on website
Oregon
  Final spend approved by NOAA Grants – 12/9/2021
  Postcards mailed to participants – In progress
  Application available on website – In progress
  Application deadline – 10/31/2022
Guam
  Final spend approved by NOAA Grants – 10/18/2021
  Notifications to participants – July 2021
  Application available on website – n/a, territory solicited apps
  Application deadline – 8/30/2021
CNMI
  Final spend approved by NOAA Grants – 5/6/2022
  Notifications to participants – May 2022
  Application available on website – n/a, territory solicited apps
  Application deadline – 6/16/2022
American Samoa
  Final spend approved by NOAA Grants – 6/17/2022
  Notifications to participants – June 2022
  Application available on website – n/a, territory solicited apps
  Application deadline – 8/2/2022

## Slide 17: CARES Act Round 2 – Back End Process
Application received at PSMFC office (electronically and via mail)
Paper applications stamped “Date Received”
Every application is reviewed for:
  Received by deadline
  Completeness
  Meet criteria/eligibility of agency spend plan
  Accuracy
  Incomplete applications are given timeline to respond with corrections/additional information
  Additional information/amended applications matched to original application
Application information entered into database for allocation purposes
Once all applications are processed, allocation of funds based on spend plan is performed
Disbursement data is submitted to Accounting for disbursement
Checks mailed

## Slide 18: CHALLENGES AND COMMON ISSUES
Unfamiliarity with spend plans
Incomplete applications
  Missing or incomplete affidavit
  Errors or omissions
  Excessive rounding
  Applicant criteria not met
  W-9 data incorrect
Working around fishing seasons
Reliant on US Postal Service; postal delivery is critical to schedule
Subaward monitoring - COVID’s impact on travel

## Slide 19: QUESTIONS?